## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000063 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-227 | EQ-1000-71433 | 1 | Very High | MP-1000-048 | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-08 | 2025-02-13 00:00 | 2025-02-15 05:00 | 2025-02-13 00:00 | 2025-02-14 12:00 | 11225.09 | 11323.61 | 72.6 | 110.3 | NONE
40100000064 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-PUMP-193 | EQ-1000-40005 | 3 | Medium |  | CALI | Calibration | PCNF | Partially Confirmed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-08 | 2025-02-22 00:00 | 2025-02-22 04:00 | 2025-02-22 03:35 |  | 14618.05 |  | 92 |  | OVER | DSGN | X | NT-1000-290305
40100000065 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-546 | EQ-1000-93202 | 3 | Medium | MP-1000-011 | REPL | Replacement | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-09 | 2025-02-17 00:00 | 2025-02-17 13:00 | 2025-02-17 00:00 | 2025-02-19 14:00 | 10504.53 | 10504.53 | 39.9 | 52.1 | NONE
40100000066 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-395 | EQ-1000-96846 | 3 | Medium | MP-1000-050 | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-06 | 2025-02-20 00:00 | 2025-02-23 00:00 | 2025-02-20 00:00 | 2025-02-20 06:00 | 2657.46 | 2891.97 | 31.8 | 35.2 | NONE
40100000067 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-573 | EQ-1000-64165 | 3 | Medium | MP-1000-036 | CLEA | Cleaning | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-03 | 2025-02-07 00:00 | 2025-02-09 20:00 | 2025-02-07 00:00 | 2025-02-09 00:00 | 15822.51 | 15822.51 | 91.7 | 91.7 | NONE
40100000066 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-815 | EQ-1000-73532 | 3 | Medium | MP-1000-008 | CALI | Calibration | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-03 | 2025-02-04 00:00 | 2025-02-05 08:00 | 2025-02-04 04:52 | 2025-02-05 02:52 | 13995.56 | 15317.36 | 67.2 | 67.2 | NONE
40100000069 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-610 | EQ-1000-48254 | 4 | Low | MP-1000-036 | TEST | Testing | DLT | Deleted | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-07 | 2025-02-19 00:00 | 2025-02-20 12:00 |  |  | 20950.74 |  | 117.7 |  | NONE
40100000070 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-713 | EQ-1000-76616 | 2 | High |  | TEST | Testing | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-08 | 2025-02-11 00:00 | 2025-02-11 10:00 | 2025-02-11 00:00 | 2025-02-12 13:00 | 8826.94 | 9551.32 | 95 | 95.9 | CORR | AGE |  | NT-1000-255813
40100000071 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-CONV-651 | EQ-1000-73483 | 2 | High |  | TEST | Testing | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-05 | 2025-02-11 00:00 | 2025-02-14 00:00 | 2025-02-11 00:00 | 2025-02-13 23:00 | 11655.94 | 12113.36 | 40 | 42.1 | WEAR | UNKN | X | NT-1000-997594
40100000072 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-CONV-144 | EQ-1000-51704 | 2 | High | MP-1000-038 | OVHL | Overhaul | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-08 | 2025-02-16 00:00 | 2025-02-18 02:00 | 2025-02-16 05:35 | 2025-02-18 08:35 | 12635.55 | 13249.95 | 6.4 | 6.6 | NONE
40100000073 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-CONV-202 | EQ-1000-78937 | 3 | Medium |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-06 | 2025-02-07 00:00 | 2025-02-07 20:00 | 2025-02-07 00:00 | 2025-02-09 06:00 | 2333.29 | 2333.29 | 94.2 | 121.6 | CORR | MATL | X | NT-1000-993140
40100000074 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-TURB-972 | EQ-1000-98389 | 3 | Medium | MP-1000-041 | CLEA | Cleaning | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-09 | 2025-02-21 02:00 | 2025-02-20 02:00 | 2025-02-18 00:00 | 2025-02-19 18:00 | 21873.38 | 21873.38 | 6.2 | 6.2 | NONE
40100000075 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-864 |  | 3 | Medium | MP-1000-004 | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-06 | 2025-02-08 00:00 | 2025-02-08 14:00 | 2025-02-08 00:00 | 2025-02-10 10:00 | 17503.03 | 19613.4 | 108.6 | 127.4 | NONE
40100000076 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-541 | EQ-1000-29080 | 2 | High | MP-1000-040 | OVHL | Overhaul | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-04 | 2025-02-13 00:00 | 2025-02-15 06:00 | 2025-02-13 08:08 | 2025-02-16 10:08 | 4664.6 | 4664.6 | 11.3 | 12.4 | NONE
40100000077 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-697 | EQ-1000-28758 | 4 | Low | MP-1000-019 | CALI | Calibration | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-04 | 2025-02-12 00:00 | 2025-02-13 10:00 | 2025-02-12 06:55 | 2025-02-14 18:55 | 16837.6 | 16837.6 | 108.1 | 108.1 | NONE