## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000078 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-552 | EQ-1000-55293 | 4 | Low | MP-1000-031 | CLEA | Cleaning | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-14 | 2025-02-19 00:00 | 2025-02-21 08:00 | 2025-02-19 08:09 | 2025-02-20 18:09 | 21209.95 | 23938.59 | 25.5 | 26 | NONE
40100000079 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-685 | EQ-1000-57049 | 3 | Medium | MP-1000-037 | INSP | Inspection | CRTD | Created | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-14 | 2025-02-19 00:00 | 2025-02-20 15:00 |  |  | 24459.64 |  | 79.7 |  | NONE
40100000080 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-863 | EQ-1000-75107 | 1 | Very High |  | REPL | Replacement | REL | Released | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-16 | 2025-02-21 00:00 | 2025-02-22 07:00 |  |  | 5865.61 |  | 24.4 |  | CORR | UNKN |  | NT-1000-758765
40100000081 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-742 | EQ-1000-94717 | 3 | Medium | MP-1000-048 | REPL | Replacement | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-10 | 2025-02-15 00:00 | 2025-02-17 10:00 | 2025-02-15 02:57 | 2025-02-15 08:57 | 18442.81 | 18688.67 | 12.6 | 12.6 | NONE
40100000082 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-COMP-235 | EQ-1000-80701 | 2 | High |  | CALI | Calibration | DLT | Deleted | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-12 | 2025-02-21 00:00 | 2025-02-23 18:00 |  |  | 20846.58 |  | 32.3 |  | NOIS | MATL | X | NT-1000-591081
40100000083 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-244 | EQ-1000-39571 | 4 | Low | MP-1000-008 | REPL | Replacement | CRTD | Created | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-16 | 2025-02-27 00:00 | 2025-03-01 04:00 |  |  | 2712.42 |  | 48.6 |  | NONE
40100000084 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-TURB-698 | EQ-1000-59941 | 3 | Medium |  | REPR | Repair | DLT | Deleted | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-16 | 2025-02-27 00:00 | 2025-03-01 01:00 |  |  | 17033.5 |  | 57.6 |  | NONE | MATL | X | NT-1000-766269
40100000085 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-817 | EQ-1000-49608 | 3 | Medium | MP-1000-008 | OVHL | Overhaul | DLT | Deleted | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-15 | 2025-02-22 00:00 | 2025-02-22 16:00 |  |  | 1611 |  | 6.4 |  | NONE
40100000086 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-238 | EQ-1000-60940 | 3 | Medium |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-13 | 2025-02-19 00:00 | 2025-02-21 23:00 | 2025-02-19 00:00 | 2025-02-21 07:00 | 22192.64 | 29360.36 | 79.3 | 79.3 | NOIS | ENVR |  | NT-1000-823811
40100000087 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-TURB-322 | EQ-1000-68115 | 4 | Low | MP-1000-042 | REPR | Repair | CRTD | Created | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-13 | 2025-02-17 00:00 | 2025-02-19 00:00 |  |  | 24532.73 |  | 45.3 |  | NONE
40100000088 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-382 | EQ-1000-34878 | 4 | Low | MP-1000-022 | LUBR | Lubrication | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-10 | 2025-02-24 00:00 | 2025-02-26 12:00 | 2025-02-24 13:08 | 2025-02-25 02:08 |  | 16221.76 | 72.5 | 72.5 | NONE
40100000089 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-310 | EQ-1000-18992 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-16 | 2025-03-01 00:00 | 2025-03-04 00:00 | 2025-03-01 00:00 | 2025-03-02 04:00 |  | 20419.8 | 29.5 | 33.1 | OVER | ENVR |  | NT-1000-666456
40100000090 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-TURB-917 | EQ-1000-32871 | 3 | Medium | MP-1000-021 | OVHL | Overhaul | PCNF | Partially Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-10 | 2025-02-21 00:00 | 2025-02-21 05:00 | 2025-02-21 00:00 |  | 864.08 |  | 95.2 |  | NONE
40100000091 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-TURB-153 | EQ-1000-26614 | 4 | Low |  | REPR | Repair | CRTD | Created | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-15 | 2025-02-22 00:00 | 2025-02-24 21:00 |  |  | 18768.8 |  | 58.2 |  | ELEC | ENVR | X | NT-1000-744986
40100000092 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-844 | EQ-1000-96363 | 3 | Medium | MP-1000-007 | INSP | Inspection | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-14 | 2025-02-19 00:00 | 2025-02-21 12:00 | 2025-02-19 10:59 | 2025-02-19 15:59 | 24965.38 | 24965.38 | 102 | 134.7 | NONE
40100000093 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-PUMP-182 | EQ-1000-52219 | 4 | Low |  | CALI | Calibration | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-14 | 2025-02-17 00:00 | 2025-02-17 10:00 | 2025-02-17 00:00 | 2025-02-17 18:00 | 15795.78 | 15795.78 | 71.1 | 73.1 | ELEC | DSGN | X | NT-1000-575755