## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000047 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-323 | EQ-1000-70952 | 4 | Low | MP-1000-050 | OVHL | Overhaul | PCNF | Partially Confirmed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-01 | 2025-02-06 00:00 | 2025-02-08 01:00 | 2025-02-06 10:27 |  | 15344.37 |  | 115.7 |  | NONE
40100000048 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-692 | EQ-1000-13365 | 3 | Medium | MP-1000-007 | LUBR | Lubrication | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-29 | 2025-02-08 00:00 | 2025-02-10 02:00 | 2025-02-08 00:18 | 2025-02-10 04:18 | 2361.91 | 2361.91 | 83.5 | 83.5 | NONE
40100000049 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-924 | EQ-1000-25866 | 4 | Low | MP-1000-001 | TEST | Testing | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-02 | 2025-02-12 00:00 | 2025-02-12 07:00 | 2025-02-12 00:08 | 2025-02-13 22:08 | 16707.27 | 18892.37 | 10.1 | 13.5 | NONE
40100000050 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-PUMP-543 | EQ-1000-57472 | 3 | Medium | MP-1000-040 | TEST | Testing | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-01 | 2025-02-15 00:00 | 2025-02-17 12:00 | 2025-02-15 00:02 | 2025-02-15 21:02 | 4815.36 | 4815.36 | 63.6 | 76.4 | NONE
40100000051 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-546 | EQ-1000-87656 | 1 | Very High |  | CALI | Calibration | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-29 | 2025-02-04 00:00 | 2025-02-05 09:00 | 2025-02-04 00:00 | 2025-02-04 13:00 | 22099.96 | 22099.96 | 30.8 | 30.8 | NOIS | ENVR |  | NT-1000-130094
40100000052 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-971 | EQ-1000-52600 | 1 | Very High | MP-1000-045 | REPL | Replacement | CRTD | Created | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-28 | 2025-02-05 00:00 | 2025-02-06 05:00 |  |  | 20046.89 |  | 42.2 |  | NONE
40100000053 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-295 | EQ-1000-21221 | 2 | High | MP-1000-046 | CLEA | Cleaning | REL | Released | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-28 | 2025-02-09 00:00 | 2025-02-11 06:00 |  |  | 14101.82 |  | 30.4 |  | NONE
40100000054 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-195 | EQ-1000-48566 | 3 | Medium |  | REPL | Replacement | CNF | Confirmed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-28 | 2025-02-04 00:00 | 2025-02-05 09:00 | 2025-02-04 02:08 | 2025-02-05 19:08 | 12094.88 | 12094.88 | 64.6 | 70.6 | BLOC | UNKN |  | NT-1000-384076
40100000055 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-357 | EQ-1000-40217 | 3 | Medium | MP-1000-013 | REPR | Repair | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-27 | 2025-02-08 00:00 | 2025-02-09 02:00 | 2025-02-08 08:10 | 2025-02-10 02:10 | 18700.59 | 21025.35 | 114.2 | 120.3 | NONE
40100000056 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-841 | EQ-1000-87278 | 3 | Medium |  | LUBR | Lubrication | CNF | Confirmed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-02 | 2025-02-11 00:00 | 2025-02-12 14:00 | 2025-02-11 02:39 | 2025-02-11 16:39 | 7758.04 | 7758.04 | 44.6 | 45.8 | CORR | AGE |  | NT-1000-147726
40100000057 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-666 | EQ-1000-48290 | 4 | Low | MP-1000-012 | INSP | Inspection | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-01 | 2025-02-04 00:00 | 2025-02-06 16:00 | 2025-02-04 00:00 | 2025-02-04 15:00 | 14564.57 | 18193.99 | 57.4 | 57.4 | NONE
40100000058 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-216 | EQ-1000-18564 | 3 | Medium | MP-1000-006 | INSP | Inspection | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-30 | 2025-02-07 00:00 | 2025-02-07 11:00 | 2025-02-07 00:00 | 2025-02-10 03:00 | 4217.31 | 4217.31 | 97.7 | 120.5 | NONE
40100000059 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-HEAT-882 | EQ-1000-64548 | 3 | Medium |  | TEST | Testing | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-31 | 2025-02-10 00:00 | 2025-02-11 06:00 | 2025-02-10 00:00 | 2025-02-12 20:00 | 11537.6 | 14728.41 | 54.2 | 54.2 | BLOC | MATL | X | NT-1000-899787
40100000060 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-740 | EQ-1000-37659 | 1 | Very High | MP-1000-027 | OVHL | Overhaul | REL | Released | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-29 | 2025-02-09 00:00 | 2025-02-09 12:00 |  |  | 6376.7 |  | 67.1 |  | NONE
40100000061 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-133 | EQ-1000-40340 | 1 | Very High | MP-1000-041 | REPR | Repair | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-29 | 2025-02-10 00:00 | 2025-02-11 14:00 | 2025-02-10 00:00 | 2025-02-12 12:00 | 17340.93 | 17340.93 | 111 | 158.1 | NONE
40100000062 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-217 | EQ-1000-81376 | 3 | Medium | MP-1000-048 | OVHL | Overhaul | TECO | Technically Complete | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-28 | 2025-02-08 00:00 | 2025-02-08 21:00 | 2025-02-08 00:00 | 2025-02-09 12:00 | 2249.54 | 2249.54 | 21.6 | 29.7 | NONE