## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000156 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-211 | EQ-1000-90698 | 3 | Medium |  | INSP | Inspection | CNF | Confirmed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-22 | 2025-04-01 00:00 | 2025-04-02 08:00 | 2025-04-01 03:33 | 2025-04-02 12:33 | 16910.93 | 16910.93 | 64.7 | 72.2 | WEAR | AGE |  | NT-1000-205428
40100000157 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-105 | EQ-1000-82135 | 4 | Low |  | LUBR | Lubrication | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-18 | 2025-03-28 14:00 | 2025-03-27 14:00 | 2025-03-25 00:00 | 2025-03-27 15:00 | 19019.82 | 19019.82 | 35.9 | 35.9 | CORR | UNKN |  | NT-1000-661147
40100000158 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-279 | EQ-1000-64773 | 3 | Medium |  | CLEA | Cleaning | CNF | Confirmed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-23 | 2025-03-26 00:00 | 2025-03-26 06:00 | 2025-03-26 00:00 | 2025-03-28 04:00 |  | 6397.74 | 90.4 | 90.4 | CORR | AGE |  | NT-1000-451317
40100000159 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-565 | EQ-1000-94058 | 4 | Low | MP-1000-047 | CLEA | Cleaning | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-21 | 2025-03-30 00:00 | 2025-04-01 17:00 | 2025-03-30 10:10 | 2025-03-31 05:10 | 7184.51 | 8231.82 | 97.4 | 101.7 | NONE
40100000160 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-114 | EQ-1000-54185 | 2 | High | MP-1000-028 | OVHL | Overhaul | CRTD | Created | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-23 | 2025-03-28 00:00 | 2025-03-29 02:00 |  |  | 15468.39 |  | 77.4 |  | NONE
40100000161 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-510 | EQ-1000-97720 | 3 | Medium | MP-1000-029 | REPL | Replacement | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-17 | 2025-03-20 00:00 | 2025-03-20 19:00 | 2025-03-20 00:00 | 2025-03-22 15:00 | 23427.72 | 23427.72 | 2.8 | 2.8 | NONE
40100000162 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-696 | EQ-1000-85088 | 1 | Very High | MP-1000-044 | INSP | Inspection | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-17 | 2025-03-22 00:00 | 2025-03-24 00:00 | 2025-03-22 00:36 | 2025-03-23 08:36 | 16860.76 | 17356.07 | 56.9 | 56.9 | NONE
40100000163 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-754 | EQ-1000-48671 | 3 | Medium | MP-1000-024 | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-19 | 2025-03-29 00:00 | 2025-03-30 06:00 | 2025-03-29 00:00 | 2025-03-30 06:00 | 12215.46 | 13180.98 | 55.7 | 76.5 | NONE
40100000164 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-921 | EQ-1000-97044 | 2 | High | MP-1000-037 | REPR | Repair | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-23 | 2025-03-27 00:00 | 2025-03-28 09:00 | 2025-03-27 09:25 | 2025-03-30 15:25 | 13374.91 | 13374.91 | 64.3 | 64.3 | NONE
40100000165 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-617 | EQ-1000-36497 | 1 | Very High |  | OVHL | Overhaul | PCNF | Partially Confirmed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-21 | 2025-03-30 00:00 | 2025-03-30 21:00 | 2025-03-30 00:00 |  | 8538.88 |  | 63.4 |  | VIBR | UNKN |  | NT-1000-195359
40100000166 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-556 | EQ-1000-17292 | 2 | High | MP-1000-020 | CLEA | Cleaning | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-20 | 2025-03-23 00:00 | 2025-03-25 19:00 | 2025-03-23 01:11 | 2025-03-25 08:11 | 14315.82 | 14315.82 | 67.9 | 67.9 | NONE
40100000167 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-CONV-360 | EQ-1000-10395 | 2 | High | MP-1000-005 | TEST | Testing | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-22 | 2025-03-26 00:00 | 2025-03-26 11:00 | 2025-03-26 12:29 | 2025-03-26 19:29 | 8940.96 | 8940.96 | 9.5 | 10.2 | NONE
40100000168 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-518 | EQ-1000-33590 | 1 | Very High | MP-1000-006 | TEST | Testing | CNF | Confirmed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-23 | 2025-03-26 00:00 | 2025-03-28 07:00 | 2025-03-26 01:04 | 2025-03-28 02:04 | 11489.16 | 11489.16 | 110.2 | 118.4 | NONE
40100000169 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-221 | EQ-1000-33392 | 3 | Medium |  | LUBR | Lubrication | CNF | Confirmed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-21 | 2025-03-28 00:00 | 2025-03-30 21:00 | 2025-03-28 00:00 | 2025-03-28 18:00 | 20953.13 | 21715.36 | 91.2 | 99 | CORR | DSGN |  | NT-1000-657772
40100000170 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-943 | EQ-1000-40102 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-18 | 2025-03-26 00:00 | 2025-03-27 22:00 | 2025-03-26 00:00 | 2025-03-26 21:00 | 5117.77 | 5661.09 | 105.3 | 105.3 | VIBR | AGE |  | NT-1000-352356