## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000016 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-109 | EQ-2000-73518 | 3 | Medium | MP-2000-029 | CLEA | Cleaning | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-14 | 2025-01-18 00:00 | 2025-01-20 03:00 | 2025-01-18 00:00 | 2025-01-21 01:00 | 10523.79 | 10523.79 | 60 | 60 | NONE
40200000017 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-678 | EQ-2000-14044 | 3 | Medium | MP-2000-030 | INSP | Inspection | CNF | Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-19 | 2025-02-01 00:00 | 2025-02-02 06:00 | 2025-02-01 00:00 | 2025-02-02 15:00 | 7233.9 | 8314.38 | 65.4 | 65.4 | NONE
40200000018 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-623 | EQ-2000-24838 | 3 | Medium | MP-2000-029 | REPL | Replacement | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-17 | 2025-01-19 00:00 | 2025-01-20 12:00 | 2025-01-19 00:00 | 2025-01-21 23:00 | 13780.06 | 13780.06 | 91.3 | 109.8 | NONE
40200000019 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-204 | EQ-2000-95678 | 4 | Low | MP-2000-008 | CLEA | Cleaning | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-19 | 2025-01-23 00:00 | 2025-01-24 16:00 | 2025-01-23 00:00 | 2025-01-23 06:00 | 6938.97 | -500 | 103.7 | 103.7 | NONE
40200000020 | PM05 | Emergency Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-805 | EQ-2000-55957 | 1 | Very High |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-19 | 2025-01-31 00:00 | 2025-02-02 08:00 | 2025-01-31 00:00 | 2025-01-31 23:00 | 19728.81 | 24177.85 | 98 | 120.1 | LEAK | ENVR | X | NT-2000-439375
40200000021 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-396 | EQ-2000-85069 | 1 | Very High | MP-2000-018 | OVHL | Overhaul | CNF | Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-15 | 2025-01-29 00:00 | 2025-01-31 19:00 | 2025-01-29 00:00 | 2025-01-29 14:00 | 24087.91 | 24223.98 | 94.7 | 94.7 | NONE
40200000022 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-355 | EQ-2000-29168 | 3 | Medium | MP-2000-027 | TEST | Testing | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-18 | 2025-01-24 00:00 | 2025-01-25 09:00 | 2025-01-24 01:18 |  | 12491.74 |  | 70.1 |  | NONE
40200000023 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-748 | EQ-2000-22202 | 3 | Medium | MP-2000-050 | CLEA | Cleaning | CLSD | Closed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-16 | 2025-01-25 00:00 | 2025-01-26 13:00 | 2025-01-25 00:00 | 2025-01-27 01:00 |  | 23781.22 | 40.6 | 44.9 | NONE
40200000024 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-750 | EQ-2000-97050 | 1 | Very High | MP-2000-018 | TEST | Testing | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-18 | 2025-01-24 00:00 | 2025-01-24 10:00 | 2025-01-24 00:00 | 2025-01-26 22:00 | 5836.83 | 5889.04 | 52.7 | 52.7 | NONE
40200000025 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-660 | EQ-2000-85750 | 4 | Low | MP-2000-002 | INSP | Inspection | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-14 | 2025-01-24 00:00 | 2025-01-26 16:00 | 2025-01-24 00:00 | 2025-01-25 21:00 | 1625.6 | 1891.14 | 75.9 | 81.4 | NONE
40200000024 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-567 | EQ-2000-10088 | 3 | Medium | MP-2000-024 | OVHL | Overhaul | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-16 | 2025-01-20 00:00 | 2025-01-20 18:00 | 2025-01-20 05:42 | 2025-01-21 21:42 | 21923.37 | 27632.1 | 105.4 | 114.8 | NONE
40200000025 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-780 | EQ-2000-95054 | 2 | High | MP-2000-014 | LUBR | Lubrication | CNF | Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-14 | 2025-01-15 00:00 | 2025-01-17 04:00 | 2025-01-15 00:00 | 2025-01-16 17:00 | 11016.16 | 11016.16 | 12.8 | 15 | NONE
40200000028 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-707 | EQ-2000-39647 | 3 | Medium |  | INSP | Inspection | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-17 | 2025-01-28 00:00 | 2025-01-30 10:00 | 2025-01-28 06:46 | 2025-01-28 09:46 | 17542.13 | 17642.13 | 98.4 | 105.7 | BLOC | UNKN |  | NT-2000-501677
40200000029 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-848 | EQ-2000-23425 | 3 | Medium | MP-2000-009 | CALI | Calibration | REL | Released | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-13 | 2025-01-19 00:00 | 2025-01-21 01:00 |  |  | 3859.67 |  | 93.3 |  | NONE
40200000030 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-643 | EQ-2000-83831 | 3 | Medium | MP-2000-027 | REPL | Replacement | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-13 | 2025-01-23 00:00 | 2025-01-23 23:00 | 2025-01-23 02:23 | 2025-01-25 12:23 | 18199.58 | 19966.38 | 76.1 | 76.1 | NONE
40200000031 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-188 | EQ-2000-23168 | 3 | Medium | MP-2000-016 | TEST | Testing | DLT | Deleted | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-14 | 2025-01-27 00:00 | 2025-01-27 17:00 |  |  | 9112.62 |  | 52.7 |  | NONE