## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000171 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-727 | EQ-2000-44039 | 4 | Low | MP-2000-032 | CALI | Calibration | CNF | Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-25 | 2025-04-03 00:00 | 2025-04-04 11:00 | 2025-04-03 00:00 | 2025-04-04 08:00 | 12047.96 | 13453.11 | 74.3 | 98.5 | NONE
40200000172 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-817 | EQ-2000-58799 | 2 | High |  | CLEA | Cleaning | CNF | Confirmed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-26 | 2025-04-09 00:00 | 2025-04-11 05:00 | 2025-04-09 06:04 | 2025-04-10 19:04 | 4907.29 | 5285.57 | 17.5 | 19 | WEAR | AGE |  | NT-2000-997904
40200000173 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-300 | EQ-2000-29116 | 3 | Medium | MP-2000-041 | INSP | Inspection | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-30 | 2025-04-11 00:00 | 2025-04-11 21:00 | 2025-04-11 00:00 | 2025-04-13 14:00 | 4826.88 | 5430.89 | 61 | 67.4 | NONE
40200000174 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-407 | EQ-2000-42895 | 2 | High | MP-2000-031 | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-28 | 2025-04-11 00:00 | 2025-04-11 08:00 | 2025-04-11 03:54 | 2025-04-13 07:54 | 17418.31 | 20310.83 | 9.1 | 9.3 | NONE
40200000175 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-862 | EQ-2000-53864 | 2 | High |  | CALI | Calibration | DLT | Deleted | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-26 | 2025-04-01 00:00 | 2025-04-03 00:00 |  |  | 8931.44 |  | 50.6 |  | ELEC | UNKN |  | NT-2000-918213
40200000176 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-463 | EQ-2000-52610 | 3 | Medium | MP-2000-041 | CLEA | Cleaning | CRTD | Created | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-29 | 2025-04-07 00:00 | 2025-04-09 16:00 |  |  | 22296 |  | 47 |  | NONE
40200000177 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-531 | EQ-2000-92742 | 4 | Low | MP-2000-019 | REPR | Repair | CNF | Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-28 | 2025-04-07 00:00 | 2025-04-09 05:00 | 2025-04-07 00:00 | 2025-04-07 11:00 | 4468.99 | 4972.14 | 28.9 | 31.5 | NONE
40200000178 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-760 | EQ-2000-61833 | 1 | Very High | MP-2000-047 | CLEA | Cleaning | DLT | Deleted | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-26 | 2025-04-03 00:00 | 2025-04-05 00:00 |  |  |  |  | 23.7 |  | NONE
40200000179 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-315 | EQ-2000-31877 | 3 | Medium | MP-2000-049 | CLEA | Cleaning | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-27 | 2025-03-29 00:00 | 2025-03-29 14:00 | 2025-03-29 01:54 | 2025-03-29 11:54 | 13936.63 | 15315.06 | 5.1 | 5.1 | NONE
40200000180 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-732 | EQ-2000-30352 | 3 | Medium | MP-2000-009 | LUBR | Lubrication | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-24 | 2025-04-04 00:00 | 2025-04-06 03:00 | 2025-04-04 00:00 | 2025-04-05 17:00 | 6561.21 | 6561.21 | 35.5 | 37.1 | NONE
40200000181 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-135 | EQ-2000-96972 | 3 | Medium | MP-2000-029 | CLEA | Cleaning | CNF | Confirmed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-26 | 2025-04-09 00:00 | 2025-04-10 19:00 | 2025-04-09 00:00 | 2025-04-11 14:00 | 24387.05 | 28228.41 | 65.8 | 65.8 | NONE
40200000182 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-711 | EQ-2000-69840 | 4 | Low | MP-2000-006 | CALI | Calibration | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-29 | 2025-04-10 00:00 | 2025-04-12 09:00 | 2025-04-10 05:42 | 2025-04-13 02:42 | 22768.62 | 28610.87 | 58.8 | 60.5 | NONE
40200000183 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-522 | EQ-2000-44053 | 1 | Very High | MP-2000-032 | OVHL | Overhaul | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-25 | 2025-03-30 00:00 | 2025-03-30 03:00 | 2025-03-30 00:00 | 2025-03-30 02:00 |  | 8925.18 | 57.4 | 60.7 | NONE
40200000184 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-884 | EQ-2000-66418 | 3 | Medium | MP-2000-028 | INSP | Inspection | REL | Released | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-30 | 2025-04-04 00:00 | 2025-04-05 07:00 |  |  | 13931.2 |  | 24.3 |  | NONE
40200000185 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-832 | EQ-2000-94671 | 4 | Low | MP-2000-040 | CALI | Calibration | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-27 | 2025-04-10 00:00 | 2025-04-12 02:00 | 2025-04-10 03:55 | 2025-04-11 09:55 | 2440.64 | 3424.54 | 75.8 | 75.8 | NONE
40200000186 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-TURB-764 | EQ-2000-79722 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-30 | 2025-04-04 00:00 | 2025-04-06 06:00 | 2025-04-04 00:00 | 2025-04-05 02:00 | 4968.98 | 4968.98 | 36.2 | 44.9 | NOIS | ENVR |  | NT-2000-296911