## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000156 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-HEAT-420 | EQ-3000-36224 | 2 | High | MP-3000-041 | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-20 | 2025-03-27 00:00 | 2025-03-28 10:00 | 2025-03-27 00:00 | 2025-03-29 19:00 | 16953.23 | 17898.14 | 66.6 | 82.9 | NONE
40300000157 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-611 | EQ-3000-37912 | 2 | High |  | CALI | Calibration | REL | Released | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-22 | 2025-04-05 00:00 | 2025-04-07 13:00 |  |  | 23460.49 |  | 64.9 |  | BLOC | ENVR |  | NT-3000-481969
40300000158 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-251 | EQ-3000-41506 | 2 | High | MP-3000-014 | TEST | Testing | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-18 | 2025-04-01 16:00 | 2025-03-31 16:00 | 2025-03-30 15:01 | 2025-04-02 00:01 | 8307 | 8307 | 100 | 100 | NONE
40300000159 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-761 | EQ-3000-31048 | 2 | High | MP-3000-020 | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-19 | 2025-03-30 00:00 | 2025-03-31 08:00 | 2025-03-30 00:00 | 2025-04-01 05:00 | 3282.19 | 3905.74 | 24.6 | 25.1 | NONE
40300000160 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-546 | EQ-3000-65314 | 2 | High |  | OVHL | Overhaul | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-22 | 2025-03-23 00:00 | 2025-03-24 03:00 |  |  | 7181.44 |  | 5.4 |  | CORR | UNKN |  | NT-3000-857568
40300000161 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-901 | EQ-3000-12609 | 3 | Medium | MP-3000-024 | CALI | Calibration | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-17 | 2025-03-31 00:00 | 2025-03-31 12:00 | 2025-03-31 00:00 | 2025-04-01 18:00 | 21745.71 | 28296.72 | 108.3 | 108.3 | NONE
40300000162 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-959 | EQ-3000-28423 | 3 | Medium | MP-3000-034 | REPR | Repair | PCNF | Partially Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-18 | 2025-03-20 00:00 | 2025-03-22 18:00 | 2025-03-20 00:00 |  | 13287.96 |  | 99.8 |  | NONE
40300000163 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-343 | EQ-3000-88619 | 3 | Medium |  | TEST | Testing | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-17 | 2025-03-30 00:00 | 2025-03-31 18:00 | 2025-03-30 04:02 | 2025-04-01 00:02 | 20243.12 | 23032.13 | 89.8 | 89.8 | BLOC | OPER | X | NT-3000-387883
40300000164 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-518 | EQ-3000-43332 | 3 | Medium | MP-3000-035 | CLEA | Cleaning | PCNF | Partially Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-23 | 2025-04-02 00:00 | 2025-04-02 09:00 | 2025-04-02 00:00 |  | 13570.01 |  | 84.6 |  | NONE
40300000165 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-384 | EQ-3000-28993 | 4 | Low |  | INSP | Inspection | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-19 | 2025-03-27 00:00 | 2025-03-29 01:00 | 2025-03-27 11:48 | 2025-03-29 04:48 | 16312.24 | 16312.24 | 108.8 | 119.9 | LEAK | UNKN |  | NT-3000-365271
40300000166 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-493 | EQ-3000-50536 | 4 | Low | MP-3000-001 | REPR | Repair | REL | Released | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-22 | 2025-04-03 00:00 | 2025-04-05 00:00 |  |  | 13605.31 |  | 29.9 |  | NONE
40300000167 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-192 | EQ-3000-40862 | 3 | Medium |  | REPL | Replacement | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-19 | 2025-03-23 00:00 | 2025-03-23 22:00 | 2025-03-23 00:00 | 2025-03-25 10:00 | 22046.95 | 27023.73 | 92.5 | 120.1 | BLOC | AGE |  | NT-3000-593975
40300000168 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-961 | EQ-3000-53610 | 4 | Low |  | CALI | Calibration | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-22 | 2025-03-29 00:00 | 2025-03-29 14:00 | 2025-03-29 05:35 | 2025-03-30 03:35 | 12905.2 | 16318.24 | 43.5 | 43.5 | NONE | UNKN | X | NT-3000-898989
40300000169 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-756 | EQ-3000-94094 | 2 | High |  | INSP | Inspection | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-18 | 2025-03-29 00:00 | 2025-03-31 10:00 | 2025-03-29 02:55 | 2025-03-29 21:55 | 10316.22 | -500 | 76.1 | 77.1 | ELEC | ENVR |  | NT-3000-641448
40300000170 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-967 | EQ-3000-87858 | 4 | Low |  | CLEA | Cleaning | CNF | Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-22 | 2025-03-29 00:00 | 2025-03-30 18:00 | 2025-03-29 00:00 | 2025-03-31 11:00 | 21900.89 | 26878.19 | 17.8 | 17.8 | OVER | UNKN | X | NT-3000-308314