## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000171 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-524 | EQ-3000-58182 | 1 | Very High |  | LUBR | Lubrication | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-25 | 2025-04-01 00:00 | 2025-04-03 02:00 | 2025-04-01 01:40 | 2025-04-04 04:40 | 1008 | 1008.51 | 4.7 | 4.7 | NONE | UNKN | X | NT-3000-584887
40300000172 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-368 | EQ-3000-32119 | 3 | Medium |  | CALI | Calibration | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-24 | 2025-03-31 00:00 | 2025-04-02 08:00 | 2025-03-31 20:09 | 2025-04-04 02:09 | 4156.65 | 4176.17 | 115 | 115 | OVER | ENVR | X | NT-3000-910926
40300000173 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-947 | EQ-3000-98291 | 1 | Very High |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-27 | 2025-03-29 00:00 | 2025-03-30 06:00 | 2025-03-30 01:08 | 2025-03-31 05:08 | 23678.28 | 25041.51 | 98 | 128.2 | CORR | MATL |  | NT-3000-552259
40300000174 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-714 | EQ-3000-38254 | 2 | High | MP-3000-017 | OVHL | Overhaul | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-30 | 2025-04-04 00:00 | 2025-04-05 02:00 | 2025-04-04 15:36 | 2025-04-06 22:36 | 10508.84 | 11242.11 | 19.2 | 20.1 | NONE
40300000175 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-478 | EQ-3000-86402 | 3 | Medium |  | INSP | Inspection | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-29 | 2025-04-09 00:00 | 2025-04-11 12:00 | 2025-04-09 20:45 | 2025-04-10 08:45 | 11987.6 | 13931.96 | 104.8 | 125.8 | BLOC | UNKN | X | NT-3000-871861
40300000176 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-362 | EQ-3000-19575 | 1 | Very High |  | REPL | Replacement | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-24 | 2025-04-02 00:00 | 2025-04-02 09:00 | 2025-04-02 11:29 | 2025-04-02 19:29 | 23311.08 | 30549.3 | 57.6 | 68.5 | ELEC | ENVR |  | NT-3000-105621
40300000177 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-616 | EQ-3000-91219 | 2 | High | MP-3000-017 | OVHL | Overhaul | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-27 | 2025-04-01 00:00 | 2025-04-03 04:00 | 2025-04-01 08:16 | 2025-04-03 09:16 | 24217.42 | 27431.06 | 68 | 78.8 | NONE
40300000178 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-TURB-998 |  | 4 | Low | MP-3000-009 | TEST | Testing | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-25 | 2025-03-27 00:00 | 2025-03-28 18:00 | 2025-03-27 21:18 | 2025-03-30 18:18 | 3974 | 3974 | 15.8 | 17.8 | NONE
40300000179 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-540 | EQ-3000-47083 | 3 | Medium |  | REPL | Replacement | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-26 | 2025-04-05 00:00 | 2025-04-06 11:00 | 2025-04-05 00:00 | 2025-04-07 20:00 | 11176.5 | 11176.5 | 21.5 | 21.5 | NOIS | OPER |  | NT-3000-155807
40300000180 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-252 |  | 4 | Low |  | CALI | Calibration | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-25 | 2025-03-28 00:00 | 2025-03-28 06:00 | 2025-03-28 00:00 | 2025-03-30 14:00 | 4507.1 | 4507.1 | 57.1 | 77.3 | VIBR | DSGN |  | NT-3000-579995
40300000181 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-215 | EQ-3000-29405 | 3 | Medium |  | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-24 | 2025-03-30 00:00 | 2025-03-30 13:00 | 2025-03-30 15:07 | 2025-03-31 19:07 | 4926.05 | 4926.05 | 21.9 | 23.4 | NONE | MATL | X | NT-3000-711893
40300000182 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-638 | EQ-3000-84814 | 3 | Medium | MP-3000-044 | CLEA | Cleaning | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-25 | 2025-04-01 00:00 | 2025-04-01 11:00 | 2025-04-01 03:21 | 2025-04-02 12:21 |  | 20323.17 | 106.7 | 106.7 | NONE
40300000183 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-482 | EQ-3000-87376 | 3 | Medium |  | INSP | Inspection | CNF | Confirmed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-24 | 2025-04-07 00:00 | 2025-04-08 19:00 | 2025-04-07 16:32 | 2025-04-08 13:32 | 2486.05 | 2934.97 | 100 | 119.3 | NOIS | DSGN |  | NT-3000-445429
40300000184 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-771 | EQ-3000-91574 | 2 | High | MP-3000-048 | INSP | Inspection | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-27 | 2025-04-02 00:00 | 2025-04-02 18:00 | 2025-04-02 13:06 | 2025-04-03 18:06 | 20138.17 | 20138.17 | 35.4 | 35.4 | NONE
40300000185 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-508 | EQ-3000-43444 | 3 | Medium | MP-3000-026 | REPR | Repair | CRTD | Created | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-25 | 2025-03-29 00:00 | 2025-03-31 05:00 |  |  | 1002.54 |  | 26.6 |  | NONE
40300000186 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-405 | EQ-3000-74336 | 2 | High |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-30 | 2025-04-06 00:00 | 2025-04-07 17:00 | 2025-04-06 05:08 | 2025-04-09 12:08 | 9296.58 | 9858.86 | 13.3 | 15.8 | ELEC | ENVR | X | NT-3000-599583