## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000109 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-CONV-562 | EQ-1000-14929 | 4 | Low |  | REPR | Repair | REL | Released | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-24 | 2025-03-02 00:00 | 2025-03-03 14:00 |  |  | 16294.33 |  | 117.3 |  | VIBR | ENVR | X | NT-1000-708519
40100000110 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-910 | EQ-1000-15376 | 4 | Low | MP-1000-022 | CLEA | Cleaning | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-27 | 2025-03-12 00:00 | 2025-03-13 02:00 | 2025-03-12 00:00 | 2025-03-13 19:00 | 12783.5 | 12783.5 | 115 | 115 | NONE
40100000111 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-761 | EQ-1000-32617 | 3 | Medium | MP-1000-050 | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-24 | 2025-02-28 00:00 | 2025-03-02 10:00 | 2025-02-28 00:00 | 2025-03-02 10:00 | 9415.5 | 10617.96 | 110.3 | 110.3 | NONE
40100000112 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-TURB-167 | EQ-1000-53213 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-24 | 2025-03-05 00:00 | 2025-03-07 03:00 | 2025-03-05 00:00 | 2025-03-06 14:00 | 18231.47 | -500 | 79.5 | 79.5 | OVER | MATL | X | NT-1000-466813
40100000113 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-771 | EQ-1000-96787 | 3 | Medium | MP-1000-009 | CALI | Calibration | CRTD | Created | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-27 | 2025-03-02 00:00 | 2025-03-02 12:00 |  |  | 14193.59 |  | 77.9 |  | NONE
40100000114 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-620 | EQ-1000-57425 | 2 | High |  | LUBR | Lubrication | CNF | Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-24 | 2025-03-02 00:00 | 2025-03-03 17:00 | 2025-03-02 01:13 | 2025-03-03 02:13 | 8872.44 | 11117.8 | 92.4 | 113.3 | WEAR | OPER |  | NT-1000-410160
40100000115 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-619 | EQ-1000-80748 | 3 | Medium | MP-1000-039 | INSP | Inspection | REL | Released | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-02 | 2025-03-14 00:00 | 2025-03-16 21:00 |  |  | 16717.27 |  | 105.4 |  | NONE
40100000116 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-285 | EQ-1000-91885 | 3 | Medium |  | TEST | Testing | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-02 | 2025-03-05 00:00 | 2025-03-07 10:00 | 2025-03-05 00:00 | 2025-03-05 07:00 | 9425.34 | 9425.34 | 86.9 | 86.9 | NOIS | ENVR |  | NT-1000-345369
40100000117 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-344 | EQ-1000-50562 | 3 | Medium | MP-1000-050 | REPL | Replacement | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-02 | 2025-03-15 00:00 | 2025-03-17 14:00 | 2025-03-15 00:00 | 2025-03-16 02:00 | 17118.52 | 17189.62 | 69.3 | 74.5 | NONE
40100000118 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-640 | EQ-1000-64874 | 2 | High | MP-1000-024 | OVHL | Overhaul | PCNF | Partially Confirmed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-25 | 2025-03-11 00:00 | 2025-03-12 03:00 | 2025-03-11 00:00 |  | 21888.55 |  | 8.2 |  | NONE
40100000119 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-971 | EQ-1000-26341 | 3 | Medium | MP-1000-006 | CALI | Calibration | PCNF | Partially Confirmed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-26 | 2025-02-28 00:00 | 2025-02-28 22:00 | 2025-02-28 00:00 |  | 11508.32 |  | 62.6 |  | NONE
40100000120 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-TURB-127 | EQ-1000-64381 | 1 | Very High |  | LUBR | Lubrication | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-24 | 2025-03-03 00:00 | 2025-03-05 18:00 | 2025-03-03 01:37 | 2025-03-05 02:37 | 9961.07 | 9961.07 | 11.6 | 11.6 | WEAR | AGE | X | NT-1000-929822
40100000121 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-COMP-240 | EQ-1000-15020 | 4 | Low |  | CLEA | Cleaning | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-26 | 2025-03-12 00:00 | 2025-03-14 14:00 | 2025-03-12 00:00 | 2025-03-12 19:00 | 11490.74 | 11490.74 | 2.6 | 2.6 | VIBR | AGE | X | NT-1000-216587
40100000122 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-TURB-343 | EQ-1000-49472 | 4 | Low | MP-1000-035 | CLEA | Cleaning | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-24 | 2025-02-25 00:00 | 2025-02-26 08:00 | 2025-02-25 00:00 | 2025-02-27 07:00 | 2038.78 | 2204.95 | 100.7 | 100.7 | NONE
40100000123 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-398 | EQ-1000-66261 | 2 | High |  | TEST | Testing | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-24 | 2025-03-08 23:00 | 2025-03-07 23:00 | 2025-03-06 03:25 | 2025-03-07 11:25 | 5089.19 | 5089.19 | 80.8 | 80.8 | NONE | MATL |  | NT-1000-509420
40100000124 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-144 | EQ-1000-93318 | 3 | Medium | MP-1000-041 | REPL | Replacement | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-27 | 2025-03-05 00:00 | 2025-03-06 10:00 | 2025-03-05 00:00 | 2025-03-05 04:00 | 19818.74 | 19818.74 | 42.7 | 42.7 | NONE