## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000001 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-125 | EQ-1000-46048 | 4 | Low |  | REPR | Repair | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-07 | 2025-01-11 00:00 | 2025-01-11 19:00 | 2025-01-11 00:00 | 2025-01-11 15:00 | 14967.07 | 15683.02 | 5.8 | 6.4 | VIBR | OPER |  | NT-1000-688508
40100000002 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-833 | EQ-1000-95181 | 1 | Very High | MP-1000-049 | LUBR | Lubrication | DLT | Deleted | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-11 | 2025-01-20 00:00 | 2025-01-22 07:00 |  |  | 11505.62 |  | 34.8 |  | NONE
40100000003 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-TURB-384 | EQ-1000-30379 | 2 | High | MP-1000-039 | REPR | Repair | PCNF | Partially Confirmed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-07 | 2025-01-20 00:00 | 2025-01-21 21:00 | 2025-01-20 10:05 |  | 2772.27 |  | 13.4 |  | NONE
40100000004 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-649 |  | 3 | Medium | MP-1000-015 | REPL | Replacement | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-09 | 2025-01-11 00:00 | 2025-01-14 00:00 | 2025-01-11 00:00 | 2025-01-12 15:00 | 14645.13 | 14645.13 | 85.1 | 85.1 | NONE
40100000005 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-987 | EQ-1000-23238 | 3 | Medium | MP-1000-044 | OVHL | Overhaul | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-09 | 2025-01-14 00:00 | 2025-01-16 12:00 | 2025-01-14 01:53 | 2025-01-16 01:53 | 9569.43 | 9569.43 | 26.7 | 31.2 | NONE
40100000006 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-750 | EQ-1000-32431 | 3 | Medium |  | OVHL | Overhaul | CRTD | Created | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-10 | 2025-01-22 00:00 | 2025-01-23 09:00 |  |  | 11825.38 |  | 33.9 |  | NONE | OPER |  | NT-1000-961722
40100000007 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-PUMP-924 | EQ-1000-51347 | 2 | High | MP-1000-014 | LUBR | Lubrication | REL | Released | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-09 | 2025-01-14 00:00 | 2025-01-14 10:00 |  |  | 22871.84 |  | 68.9 |  | NONE
40100000008 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-CONV-758 | EQ-1000-70142 | 4 | Low |  | CALI | Calibration | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-07 | 2025-01-12 00:00 | 2025-01-12 19:00 | 2025-01-12 00:00 | 2025-01-13 09:00 | 18801.84 | 18801.84 | 52.6 | 52.6 | BLOC | MATL | X | NT-1000-195325
40100000009 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-981 | EQ-1000-24371 | 3 | Medium | MP-1000-030 | TEST | Testing | CRTD | Created | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-07 | 2025-01-18 00:00 | 2025-01-18 22:00 |  |  | 15112.02 |  | 47.4 |  | NONE
40100000010 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-HEAT-981 | EQ-1000-11504 | 2 | High |  | CALI | Calibration | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-11 | 2025-01-23 00:00 | 2025-01-23 16:00 | 2025-01-23 11:06 | 2025-01-26 09:06 | 19330.67 | 19936.29 | 42.1 | 42.1 | CORR | DSGN | X | NT-1000-624902
40100000011 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-619 | EQ-1000-23947 | 2 | High |  | LUBR | Lubrication | DLT | Deleted | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-12 | 2025-01-23 00:00 | 2025-01-24 16:00 |  |  | 4244.56 |  | 92 |  | NONE | ENVR |  | NT-1000-612340
40100000012 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-214 | EQ-1000-57576 | 5 | Unknown | MP-1000-047 | INSP | Inspection | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-12 | 2025-01-25 00:00 | 2025-01-26 17:00 | 2025-01-25 04:25 | 2025-01-26 12:25 | 6401.35 | 6565.9 | 68.9 | 70.8 | NONE
40100000013 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-884 | EQ-1000-26483 | 2 | High |  | OVHL | Overhaul | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-07 | 2025-01-18 00:00 | 2025-01-20 14:00 | 2025-01-18 00:00 | 2025-01-21 00:00 | 6993.89 | 6993.89 | 104.9 | 104.9 | BLOC | OPER |  | NT-1000-847581
40100000014 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-508 | EQ-1000-98039 | 1 | Very High |  | CLEA | Cleaning | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-11 | 2025-01-17 00:00 | 2025-01-19 10:00 | 2025-01-17 00:00 | 2025-01-19 20:00 | 3464.6 | 3782.48 | 28.5 | 35.8 | ELEC | AGE |  | NT-1000-107540
40100000015 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-824 | EQ-1000-92719 | 1 | Very High | MP-1000-014 | REPL | Replacement | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-06 | 2025-01-10 00:00 | 2025-01-10 10:00 | 2025-01-10 05:35 | 2025-01-10 11:35 | 2236.01 | 2236.01 | 30.1 | 38.2 | NONE