## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000140 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-371 | EQ-1000-95344 | 3 | Medium | MP-1000-020 | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-11 | 2025-03-24 00:00 | 2025-03-26 07:00 | 2025-03-24 00:39 | 2025-03-24 05:39 | 22280.42 | 24705.98 | 66.4 | 76.1 | NONE
40100000141 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-CONV-404 | EQ-1000-69446 | 2 | High | MP-1000-010 | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-10 | 2025-03-22 00:00 | 2025-03-22 09:00 | 2025-03-22 01:20 | 2025-03-22 23:20 | 10682.73 | 10682.73 | 56.8 | 81.1 | NONE
40100000142 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-TURB-508 | EQ-1000-27139 | 4 | Low | MP-1000-016 | REPR | Repair | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-16 | 2025-03-22 00:00 | 2025-03-24 19:00 | 2025-03-22 00:00 | 2025-03-25 01:00 | 8318.34 | 8318.34 | 57 | 60.5 | NONE
40100000143 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-PUMP-397 | EQ-1000-60351 | 3 | Medium | MP-1000-037 | LUBR | Lubrication | REL | Released | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-16 | 2025-03-26 00:00 | 2025-03-28 07:00 |  |  | 24085.8 |  | 108.5 |  | NONE
40100000144 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-881 | EQ-1000-30885 | 4 | Low |  | CLEA | Cleaning | CRTD | Created | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-13 | 2025-03-22 00:00 | 2025-03-24 13:00 |  |  | 22037.35 |  | 60.7 |  | VIBR | DSGN |  | NT-1000-711680
40100000145 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-149 | EQ-1000-16624 | 2 | High |  | INSP | Inspection | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-12 | 2025-03-20 00:00 | 2025-03-22 14:00 | 2025-03-20 06:33 | 2025-03-21 20:33 | 21255.72 | 21255.72 | 52.8 | 62.1 | CORR | UNKN |  | NT-1000-147440
40100000146 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-152 | EQ-1000-84747 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-14 | 2025-03-18 00:00 | 2025-03-20 00:00 | 2025-03-18 00:00 | 2025-03-21 00:00 | 2301.53 | 2301.53 | 61.5 | 61.6 | NONE | MATL |  | NT-1000-234913
40100000147 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-503 |  | 2 | High |  | LUBR | Lubrication | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-16 | 2025-03-22 00:00 | 2025-03-24 00:00 | 2025-03-22 00:00 | 2025-03-22 20:00 | 15260.34 | 17733.57 | 49.4 | 49.4 | LEAK | AGE |  | NT-1000-943019
40100000148 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-631 | EQ-1000-69898 | 1 | Very High | MP-1000-040 | REPL | Replacement | TECO | Technically Complete | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-11 | 2025-03-21 00:00 | 2025-03-23 19:00 | 2025-03-21 00:00 | 2025-03-21 19:00 | 23318.53 | 23318.53 | 39.6 | 62 | NONE
40100000149 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-444 | EQ-1000-76494 | 3 | Medium | MP-1000-008 | CALI | Calibration | CNF | Confirmed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-16 | 2025-03-25 00:00 | 2025-03-27 22:00 | 2025-03-25 00:21 | 2025-03-27 16:21 | 12134.87 | 12134.87 | 4 | 4.3 | NONE
40100000150 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-711 | EQ-1000-72205 | 1 | Very High | MP-1000-025 | CLEA | Cleaning | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-12 | 2025-03-23 00:00 | 2025-03-24 07:00 | 2025-03-23 00:00 | 2025-03-23 08:00 | 4677.55 | 4752.22 | 76.2 | 76.2 | NONE
40100000151 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-686 | EQ-1000-24404 | 2 | High |  | TEST | Testing | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-11 | 2025-03-12 00:00 | 2025-03-14 10:00 | 2025-03-12 09:01 | 2025-03-14 03:01 | 4210.07 | 4210.07 | 83.5 | 91.1 | BLOC | ENVR |  | NT-1000-840058
40100000152 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-631 | EQ-1000-37176 | 4 | Low | MP-1000-022 | TEST | Testing | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-14 | 2025-03-20 00:00 | 2025-03-22 15:00 | 2025-03-20 00:00 | 2025-03-22 21:00 | 8186.94 | 8186.94 | 22.4 | 22.4 | NONE
40100000153 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-724 | EQ-1000-73462 | 2 | High | MP-1000-019 | CALI | Calibration | CLSD | Closed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-11 | 2025-03-15 00:00 | 2025-03-16 13:00 | 2025-03-15 10:30 | 2025-03-18 11:30 | 6009.24 | 6009.24 | 116.8 | 123.3 | NONE
40100000154 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-424 | EQ-1000-72888 | 2 | High | MP-1000-026 | REPR | Repair | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-12 | 2025-03-21 00:00 | 2025-03-22 13:00 | 2025-03-21 00:00 | 2025-03-22 14:00 | 14550.18 | 15618.25 | 66.1 | 66.1 | NONE
40100000155 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-143 | EQ-1000-47700 | 2 | High | MP-1000-018 | CALI | Calibration | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-15 | 2025-03-17 00:00 | 2025-03-18 22:00 | 2025-03-17 04:16 | 2025-03-19 14:16 | 18809.79 | 19471.85 | 27.3 | 30 | NONE