## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000078 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-978 | EQ-2000-99764 | 2 | High | MP-2000-018 | CALI | Calibration | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-10 | 2025-02-24 00:00 | 2025-02-25 07:00 | 2025-02-24 01:59 | 2025-02-24 20:59 | 24368.38 | 27415.14 | 54.3 | 54.3 | NONE
40200000079 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-761 | EQ-2000-21703 | 3 | Medium | MP-2000-004 | TEST | Testing | DLT | Deleted | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-11 | 2025-02-19 00:00 | 2025-02-20 05:00 |  |  | 18653.15 |  | 91.6 |  | NONE
40200000080 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-418 | EQ-2000-76426 | 3 | Medium | MP-2000-004 | INSP | Inspection | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-13 | 2025-02-16 00:00 | 2025-02-18 21:00 | 2025-02-16 02:14 | 2025-02-19 04:14 | 4756.57 | 4756.57 | 105.3 | 109.4 | NONE
40200000081 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-151 | EQ-2000-57235 | 4 | Low | MP-2000-008 | REPL | Replacement | PCNF | Partially Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-15 | 2025-02-19 00:00 | 2025-02-20 13:00 | 2025-02-19 00:00 |  | 20675.9 |  | 61.6 |  | NONE
40200000082 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-481 | EQ-2000-74066 | 1 | Very High |  | REPL | Replacement | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-14 | 2025-02-22 00:00 | 2025-02-23 00:00 | 2025-02-22 03:46 | 2025-02-24 17:46 | 8934.1 | 8934.1 | 100.8 | 130.8 | CORR | UNKN |  | NT-2000-128783
40200000083 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-150 | EQ-2000-31352 | 4 | Low | MP-2000-002 | LUBR | Lubrication | CLSD | Closed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-16 | 2025-02-26 00:00 | 2025-02-27 05:00 | 2025-02-26 00:00 | 2025-02-27 06:00 | 17103.53 | 17103.53 | 33.8 | 36 | NONE
40200000084 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-235 | EQ-2000-94852 | 3 | Medium | MP-2000-046 | CALI | Calibration | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-11 | 2025-02-21 00:00 | 2025-02-21 03:00 | 2025-02-21 04:40 | 2025-02-22 10:40 | 15404.43 | 15848.19 | 113.3 | 113.3 | NONE
40200000085 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-485 | EQ-2000-55706 | 4 | Low | MP-2000-007 | CALI | Calibration | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-13 | 2025-02-18 00:00 | 2025-02-19 05:00 | 2025-02-18 00:00 | 2025-02-20 13:00 | 17091.31 | 17091.31 | 99.3 | 99.3 | NONE
40200000086 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-762 | EQ-2000-87826 | 3 | Medium | MP-2000-018 | CLEA | Cleaning | CNF | Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-14 | 2025-02-19 00:00 | 2025-02-20 16:00 | 2025-02-19 00:00 | 2025-02-19 15:00 | 2064.01 | 2064.01 | 118.6 | 118.6 | NONE
40200000087 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-253 | EQ-2000-77802 | 3 | Medium | MP-2000-042 | TEST | Testing | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-16 | 2025-02-20 00:00 | 2025-02-20 09:00 | 2025-02-20 01:30 | 2025-02-23 07:30 | 16682.99 | 16682.99 | 82.3 | 82.3 | NONE
40200000088 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-528 | EQ-2000-63031 | 1 | Very High | MP-2000-041 | LUBR | Lubrication | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-13 | 2025-02-25 00:00 | 2025-02-25 06:00 | 2025-02-25 02:47 | 2025-02-28 06:47 | 8907.59 | 10135.6 | 86.2 | 86.2 | NONE
40200000089 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-407 | EQ-2000-32280 | 4 | Low | MP-2000-036 | REPR | Repair | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-16 | 2025-02-27 00:00 | 2025-02-28 01:00 | 2025-02-27 00:00 | 2025-02-28 15:00 | 12034.13 | 12034.13 | 89.4 | 89.4 | NONE
40200000090 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-327 | EQ-2000-56567 | 3 | Medium | MP-2000-019 | TEST | Testing | DLT | Deleted | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-11 | 2025-02-23 00:00 | 2025-02-24 17:00 |  |  | 19808.22 |  | 41.1 |  | NONE
40200000091 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-154 | EQ-2000-93151 | 4 | Low | MP-2000-025 | CLEA | Cleaning | PCNF | Partially Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-14 | 2025-02-24 00:00 | 2025-02-24 11:00 | 2025-02-24 00:00 |  | 22290.94 |  | 61.1 |  | NONE
40200000092 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-155 | EQ-2000-29762 | 4 | Low | MP-2000-006 | CLEA | Cleaning | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-11 | 2025-02-15 00:00 | 2025-02-16 21:00 | 2025-02-15 08:20 | 2025-02-17 14:20 | 4008.99 | 4344.43 | 103.8 | 109.2 | NONE
40200000093 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-420 | EQ-2000-93165 | 2 | High | MP-2000-032 | LUBR | Lubrication | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-10 | 2025-02-11 00:00 | 2025-02-13 11:00 | 2025-02-11 00:00 | 2025-02-12 13:00 | 19149.24 | 20607.72 | 21.9 | 23.2 | NONE