## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000001 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-209 | EQ-2000-27758 | 3 | Medium | MP-2000-029 | REPL | Replacement | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-08 | 2025-01-09 00:00 | 2025-01-11 04:00 | 2025-01-09 05:20 |  | 21119.53 |  | 46.8 |  | NONE
40200000002 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-239 | EQ-2000-49378 | 1 | Very High |  | REPL | Replacement | CNF | Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-08 | 2025-01-18 00:00 | 2025-01-19 03:00 | 2025-01-18 02:24 | 2025-01-20 17:24 | 4852.11 | 4991.2 | 49 | 51.9 | ELEC | MATL |  | NT-2000-703853
40200000003 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-433 | EQ-2000-59290 | 3 | Medium | MP-2000-012 | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-08 | 2025-01-22 00:00 | 2025-01-24 04:00 | 2025-01-22 08:58 | 2025-01-24 08:58 | 23335.65 | 24083.43 | 25.6 | 28.2 | NONE
40200000004 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-825 | EQ-2000-37479 | 4 | Low |  | TEST | Testing | CNF | Confirmed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-09 | 2025-01-22 00:00 | 2025-01-23 15:00 | 2025-01-22 00:00 | 2025-01-22 10:00 | 16987.95 | 18536.99 | 18.4 | 20 | CORR | OPER |  | NT-2000-927406
40200000005 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-175 | EQ-2000-68860 | 4 | Low | MP-2000-035 | TEST | Testing | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-10 | 2025-01-18 00:00 | 2025-01-20 05:00 | 2025-01-18 00:00 | 2025-01-20 22:00 | 13819.31 | 13819.31 | 95.3 | 95.3 | NONE
40200000006 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-887 | EQ-2000-42536 | 3 | Medium | MP-2000-049 | INSP | Inspection | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-11 | 2025-01-22 00:00 | 2025-01-23 23:00 | 2025-01-22 01:02 | 2025-01-23 00:02 | 14298.9 | 14298.9 | 78.1 | 87.9 | NONE
40200000007 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-110 | EQ-2000-22924 | 1 | Very High | MP-2000-038 | LUBR | Lubrication | CRTD | Created | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-08 | 2025-01-12 00:00 | 2025-01-14 19:00 |  |  | 11421.57 |  | 48.2 |  | NONE
40200000008 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-125 | EQ-2000-73277 | 3 | Medium | MP-2000-022 | REPR | Repair | CLSD | Closed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-06 | 2025-01-11 00:00 | 2025-01-13 07:00 | 2025-01-11 00:00 | 2025-01-11 12:00 | 20867.28 | 26755.47 | 88.2 | 88.2 | NONE
40200000009 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-594 | EQ-2000-55652 | 4 | Low | MP-2000-002 | REPL | Replacement | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-09 | 2025-01-11 00:00 | 2025-01-13 10:00 | 2025-01-11 00:00 | 2025-01-13 11:00 | 2145.77 | 2506.86 | 7.3 | 9.6 | NONE
40200000010 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-858 | EQ-2000-41970 | 4 | Low | MP-2000-026 | OVHL | Overhaul | PCNF | Partially Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-10 | 2025-01-13 00:00 | 2025-01-16 00:00 | 2025-01-13 07:12 |  | 8609.25 |  | 52.3 |  | NONE
40200000011 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-755 | EQ-2000-96154 | 3 | Medium |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-09 | 2025-01-16 00:00 | 2025-01-16 05:00 | 2025-01-16 00:00 | 2025-01-19 08:00 | 11514.59 | 13065.41 | 52.7 | 53.2 | LEAK | UNKN |  | NT-2000-705393
40200000012 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-918 | EQ-2000-80371 | 2 | High | MP-2000-034 | LUBR | Lubrication | CRTD | Created | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-07 | 2025-01-13 00:00 | 2025-01-14 19:00 |  |  | 11709.99 |  | 33 |  | NONE
40200000013 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-497 | EQ-2000-90125 | 3 | Medium | MP-2000-046 | REPL | Replacement | CLSD | Closed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-09 | 2025-01-19 00:00 | 2025-01-19 16:00 | 2025-01-19 03:01 | 2025-01-21 01:01 | 21215.19 | 21215.19 | 74.8 | 82.6 | NONE
40200000014 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-420 | EQ-2000-25448 | 3 | Medium | MP-2000-009 | REPL | Replacement | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-07 | 2025-01-12 00:00 | 2025-01-12 16:00 | 2025-01-12 00:00 | 2025-01-13 01:00 | 17489.2 | 19175.31 | 62.3 | 82 | NONE
40200000015 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-290 | EQ-2000-73788 | 1 | Very High | MP-2000-029 | OVHL | Overhaul | CLSD | Closed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-11 | 2025-01-20 00:00 | 2025-01-21 00:00 | 2025-01-20 07:29 | 2025-01-23 08:29 | 12496.23 | 13417.34 | 18.6 | 18.6 | NONE