## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000047 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-378 | EQ-2000-40619 | 2 | High | MP-2000-027 | REPR | Repair | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-27 | 2025-01-31 00:00 | 2025-01-31 19:00 | 2025-01-31 11:29 | 2025-02-03 15:29 | 4307.56 | 4307.56 | 21.4 | 31 | NONE
40200000048 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-562 | EQ-2000-50410 | 4 | Low | MP-2000-039 | OVHL | Overhaul | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-30 | 2025-02-04 00:00 | 2025-02-04 17:00 | 2025-02-04 06:37 | 2025-02-04 19:37 | 20286.12 | 23898.16 | 37.9 | 44.6 | NONE
40200000049 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-251 | EQ-2000-21955 | 3 | Medium | MP-2000-012 | TEST | Testing | REL | Released | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-01 | 2025-02-05 00:00 | 2025-02-06 23:00 |  |  | 13079.76 |  | 81.9 |  | NONE
40200000050 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-669 | EQ-2000-82105 | 4 | Low | MP-2000-050 | REPR | Repair | CRTD | Created | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-28 | 2025-01-30 00:00 | 2025-02-01 13:00 |  |  |  |  | 18.5 |  | NONE
40200000051 | PM05 | Emergency Maintenance | 2000 | Plant B - Chicago | CHI-COMP-943 | EQ-2000-62505 | 2 | High |  | CALI | Calibration | CLSD | Closed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-29 | 2025-02-09 00:00 | 2025-02-09 12:00 | 2025-02-09 00:00 | 2025-02-12 04:00 | 22977 | 24150.89 | 10.8 | 14.4 | VIBR | OPER | X | NT-2000-196446
40200000052 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-225 | EQ-2000-15596 | 4 | Low | MP-2000-044 | TEST | Testing | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-30 | 2025-01-31 00:00 | 2025-01-31 23:00 | 2025-01-31 07:08 | 2025-02-03 10:08 |  | 20631.29 | 48.6 | 56.8 | NONE
40200000053 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-319 | EQ-2000-34530 | 2 | High | MP-2000-032 | INSP | Inspection | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-29 | 2025-02-03 00:00 | 2025-02-05 11:00 | 2025-02-03 04:12 | 2025-02-04 01:12 | 15545.61 | 15826.6 | 74.8 | 74.8 | NONE
40200000054 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-189 | EQ-2000-46670 | 3 | Medium | MP-2000-025 | LUBR | Lubrication | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-30 | 2025-02-02 00:00 | 2025-02-04 07:00 | 2025-02-02 09:34 | 2025-02-03 12:34 | 15953.48 | 15953.48 | 96.7 | 96.7 | NONE
40200000055 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-657 | EQ-2000-73527 | 3 | Medium | MP-2000-002 | TEST | Testing | CNF | Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-29 | 2025-02-08 00:00 | 2025-02-10 18:00 | 2025-02-08 00:00 | 2025-02-09 19:00 | 7125.67 | 7307.05 | 5.1 | 5.1 | NONE
40200000056 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-642 | EQ-2000-56849 | 3 | Medium | MP-2000-048 | REPR | Repair | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-02 | 2025-02-12 00:00 | 2025-02-13 07:00 | 2025-02-12 05:53 | 2025-02-13 03:53 | 6572.5 | 6572.5 | 30.5 | 30.5 | NONE
40200000057 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-966 | EQ-2000-60911 | 3 | Medium | MP-2000-038 | LUBR | Lubrication | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-29 | 2025-02-12 00:00 | 2025-02-13 00:00 | 2025-02-12 13:44 | 2025-02-13 13:44 | 15016.73 | 18272.47 | 97.1 | 97.1 | NONE
40200000058 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-677 | EQ-2000-28625 | 3 | Medium |  | CALI | Calibration | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-31 | 2025-02-04 00:00 | 2025-02-06 17:00 | 2025-02-04 03:34 | 2025-02-07 02:34 | 4801.14 | 5415.75 | 6.5 | 7.8 | LEAK | OPER |  | NT-2000-100716
40200000059 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-728 | EQ-2000-36406 | 4 | Low | MP-2000-002 | OVHL | Overhaul | REL | Released | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-02 | 2025-02-05 00:00 | 2025-02-06 21:00 |  |  | 23010.13 |  | 101.6 |  | NONE
40200000060 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-966 | EQ-2000-78982 | 2 | High | MP-2000-022 | REPL | Replacement | REL | Released | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-02 | 2025-02-08 00:00 | 2025-02-08 11:00 |  |  | 17761.18 |  | 80.1 |  | NONE
40200000061 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-261 | EQ-2000-67261 | 2 | High |  | OVHL | Overhaul | CNF | Confirmed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-02 | 2025-02-13 00:00 | 2025-02-15 16:00 | 2025-02-13 01:41 | 2025-02-14 19:41 | 17825.98 | 20422.07 | 68.3 | 68.3 | ELEC | OPER |  | NT-2000-421727
40200000062 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-TURB-230 | EQ-2000-33292 | 2 | High |  | INSP | Inspection | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-01 | 2025-02-02 00:00 | 2025-02-04 04:00 | 2025-02-02 00:00 | 2025-02-05 02:00 | 4961 | 5661.07 | 39.5 | 39.5 | WEAR | UNKN |  | NT-2000-447255