## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000187 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-119 | EQ-2000-29942 | 3 | Medium | MP-2000-001 | REPR | Repair | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-31 | 2025-04-09 00:00 | 2025-04-09 04:00 | 2025-04-09 00:00 | 2025-04-10 01:00 | 7411.81 | 8282.18 | 16.8 | 16.8 | NONE
40200000188 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-115 | EQ-2000-74694 | 3 | Medium | MP-2000-022 | CLEA | Cleaning | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-04-01 | 2025-04-07 00:00 | 2025-04-09 07:00 | 2025-04-07 00:10 | 2025-04-08 17:10 | 24950.1 | 25411.2 | 56.7 | 65.8 | NONE
40200000189 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-372 | EQ-2000-61435 | 3 | Medium | MP-2000-001 | LUBR | Lubrication | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-31 | 2025-04-09 00:00 | 2025-04-11 14:00 | 2025-04-09 00:00 | 2025-04-10 01:00 | 22444.62 | 22444.62 | 31.5 | 31.5 | NONE
40200000190 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-889 | EQ-2000-68059 | 2 | High | MP-2000-014 | CLEA | Cleaning | CNF | Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-04-01 | 2025-04-13 00:00 | 2025-04-13 06:00 | 2025-04-13 00:00 | 2025-04-14 03:00 | 18515.41 | 18515.41 | 13.1 | 13.5 | NONE
40200000191 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-TURB-430 | EQ-2000-30789 | 3 | Medium | MP-2000-004 | REPR | Repair | CNF | Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-04-05 | 2025-04-17 00:00 | 2025-04-17 07:00 | 2025-04-17 00:00 | 2025-04-20 00:00 | 6706.16 | 6713.07 | 77.3 | 97.9 | NONE
40200000192 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-341 | EQ-2000-92956 | 3 | Medium | MP-2000-003 | CALI | Calibration | CNF | Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-04-03 | 2025-04-09 00:00 | 2025-04-09 03:00 | 2025-04-09 00:00 | 2025-04-09 23:00 | 14825.07 | 14825.07 | 48.7 | 57.7 | NONE
40200000193 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-258 | EQ-2000-58679 | 3 | Medium | MP-2000-049 | OVHL | Overhaul | REL | Released | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-04-06 | 2025-04-08 00:00 | 2025-04-09 09:00 |  |  | 12748.02 |  | 82.9 |  | NONE
40200000194 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-464 | EQ-2000-94485 | 3 | Medium | MP-2000-042 | OVHL | Overhaul | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-04-01 | 2025-04-13 00:00 | 2025-04-15 22:00 | 2025-04-13 11:24 | 2025-04-14 02:24 | 12452.15 | 12452.15 | 39.4 | 39.4 | NONE