## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000094 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-536 | EQ-3000-54216 | 1 | Very High | MP-3000-021 | REPL | Replacement | PCNF | Partially Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-23 | 2025-03-09 00:00 | 2025-03-11 05:00 | 2025-03-09 02:15 |  | 3459.66 |  | 82.7 |  | NONE
40300000095 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-HEAT-277 | EQ-3000-53975 | 2 | High |  | OVHL | Overhaul | DLT | Deleted | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-17 | 2025-02-19 00:00 | 2025-02-20 13:00 |  |  | 19059.98 |  | 21.8 |  | ELEC | ENVR | X | NT-3000-239849
40300000096 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-910 | EQ-3000-92863 | 3 | Medium | MP-3000-046 | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-21 | 2025-02-28 00:00 | 2025-02-28 22:00 | 2025-02-28 23:24 | 2025-03-01 03:24 | 2477.7 | 2764.25 | 2.9 | 2.9 | NONE
40300000097 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-810 | EQ-3000-72391 | 4 | Low |  | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-22 | 2025-02-25 00:00 | 2025-02-26 04:00 | 2025-02-25 00:00 | 2025-02-25 20:00 | 13315.63 | 17465.55 | 50.6 | 50.6 | OVER | ENVR | X | NT-3000-852037
40300000098 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-726 | EQ-3000-21537 | 3 | Medium |  | TEST | Testing | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-22 | 2025-03-08 00:00 | 2025-03-09 16:00 | 2025-03-08 00:00 | 2025-03-09 22:00 | 611.97 | 706.55 | 29.8 | 36.6 | VIBR | ENVR |  | NT-3000-898100
40300000099 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-619 | EQ-3000-38740 | 1 | Very High |  | CALI | Calibration | REL | Released | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-02-20 | 2025-03-05 00:00 | 2025-03-06 04:00 |  |  | 1800.19 |  | 15.3 |  | OVER | UNKN |  | NT-3000-284888
40300000100 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-786 | EQ-3000-15651 | 3 | Medium |  | LUBR | Lubrication | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-17 | 2025-02-28 00:00 | 2025-03-02 00:00 | 2025-02-28 00:00 | 2025-03-01 14:00 | 11149.46 | 12994.82 | 41.4 | 46.8 | NOIS | AGE | X | NT-3000-265722
40300000101 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-596 | EQ-3000-77489 | 3 | Medium |  | REPL | Replacement | CLSD | Closed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-17 | 2025-02-19 00:00 | 2025-02-20 08:00 | 2025-02-19 00:00 | 2025-02-21 10:00 | 10767.12 | 12526.45 | 90.2 | 96.7 | ELEC | OPER |  | NT-3000-202827
40300000102 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-855 | EQ-3000-64079 | 2 | High |  | LUBR | Lubrication | CRTD | Created | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-23 | 2025-02-27 00:00 | 2025-03-01 02:00 |  |  | 2301.48 |  | 71 |  | LEAK | DSGN |  | NT-3000-286710
40300000103 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-482 | EQ-3000-27878 | 4 | Low | MP-3000-045 | REPL | Replacement | CRTD | Created | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-20 | 2025-03-04 00:00 | 2025-03-05 02:00 |  |  | 24401.12 |  | 25.9 |  | NONE
40300000104 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-239 | EQ-3000-24563 | 3 | Medium |  | TEST | Testing | REL | Released | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-23 | 2025-03-03 00:00 | 2025-03-05 12:00 |  |  | 4694.43 |  | 42.5 |  | CORR | ENVR |  | NT-3000-706204
40300000105 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-HEAT-975 | EQ-3000-40107 | 2 | High |  | LUBR | Lubrication | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-17 | 2025-02-24 00:00 | 2025-02-26 20:00 | 2025-02-24 16:37 | 2025-02-27 08:37 | 14993.73 | 14993.73 | 100.8 | 100.8 | CORR | AGE | X | NT-3000-359870
40300000106 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-544 | EQ-3000-85951 | 3 | Medium | MP-3000-047 | INSP | Inspection | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-18 | 2025-02-28 00:00 | 2025-02-28 21:00 |  |  | 10735.41 |  | 7.2 |  | NONE
40300000107 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-643 | EQ-3000-61684 | 3 | Medium |  | CLEA | Cleaning | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-20 | 2025-03-05 00:00 | 2025-03-05 14:00 | 2025-03-05 00:58 | 2025-03-07 11:58 | 6392.53 | 8118.79 | 67.9 | 67.9 | LEAK | UNKN |  | NT-3000-475815
40300000108 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-TURB-344 | EQ-3000-94887 | 4 | Low | MP-3000-038 | CALI | Calibration | PCNF | Partially Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-17 | 2025-02-18 00:00 | 2025-02-20 15:00 | 2025-02-18 00:00 |  | 4464.17 |  | 56.2 |  | NONE