## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000001 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-121 | EQ-3000-59514 | 2 | High |  | INSP | Inspection | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-08 | 2025-01-20 00:00 | 2025-01-20 19:00 | 2025-01-20 00:00 | 2025-01-21 10:00 | 12389.9 | 15063.68 | 53.6 | 72.7 | CORR | ENVR |  | NT-3000-670027
40300000002 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-431 | EQ-3000-71393 | 4 | Low |  | OVHL | Overhaul | DLT | Deleted | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-08 | 2025-01-22 00:00 | 2025-01-25 00:00 |  |  | 2187.48 |  | 20.3 |  | CORR | MATL |  | NT-3000-913608
40300000003 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-HEAT-488 | EQ-3000-34318 | 1 | Very High |  | REPL | Replacement | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-06 | 2025-01-16 00:00 | 2025-01-18 00:00 | 2025-01-16 05:44 | 2025-01-17 13:44 | 18164.59 | 18305.98 | 79.7 | 79.7 | NONE | DSGN | X | NT-3000-902930
40300000004 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-257 | EQ-3000-90352 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-08 | 2025-01-14 00:00 | 2025-01-16 06:00 | 2025-01-14 08:06 | 2025-01-16 03:06 | 2858.28 | 3053.59 | 79.7 | 79.7 | LEAK | OPER |  | NT-3000-212255
40300000005 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-CONV-296 | EQ-3000-22943 | 1 | Very High | MP-3000-024 | CLEA | Cleaning | REL | Released | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-06 | 2025-01-16 00:00 | 2025-01-18 03:00 |  |  | 13382.62 |  | 84.8 |  | NONE
40300000006 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-313 | EQ-3000-95950 | 4 | Low |  | INSP | Inspection | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-09 | 2025-01-23 00:00 | 2025-01-23 12:00 | 2025-01-23 00:00 | 2025-01-25 13:00 | 9342.69 | 12254.24 | 89.7 | 92.4 | BLOC | MATL |  | NT-3000-654718
40300000007 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-851 | EQ-3000-19225 | 4 | Low | MP-3000-013 | REPR | Repair | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-12 | 2025-01-17 00:00 | 2025-01-17 11:00 | 2025-01-17 04:13 | 2025-01-18 09:13 | 2980.02 | 3448.57 | 29.3 | 34.5 | NONE
40300000008 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-740 | EQ-3000-33448 | 4 | Low | MP-3000-045 | REPR | Repair | REL | Released | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-10 | 2025-01-22 00:00 | 2025-01-24 07:00 |  |  | 19273.94 |  | 70 |  | NONE
40300000009 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-270 | EQ-3000-33644 | 1 | Very High |  | REPL | Replacement | CRTD | Created | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-10 | 2025-01-17 00:00 | 2025-01-19 18:00 |  |  | 16609.53 |  | 65 |  | NOIS | MATL |  | NT-3000-985893
40300000010 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-522 | EQ-3000-93000 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-09 | 2025-01-23 00:00 | 2025-01-24 19:00 | 2025-01-23 00:00 | 2025-01-26 07:00 | 14297.05 | 15925.87 | 27.2 | 29.4 | NONE | UNKN |  | NT-3000-516379
40300000011 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-843 | EQ-3000-14543 | 3 | Medium |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-08 | 2025-01-18 00:00 | 2025-01-18 04:00 | 2025-01-18 00:00 | 2025-01-20 20:00 | 24838.59 | 29077.22 | 37.6 | 45.8 | CORR | OPER |  | NT-3000-909000
40300000012 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-666 | EQ-3000-77013 | 3 | Medium |  | INSP | Inspection | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-10 | 2025-01-20 00:00 | 2025-01-20 21:00 | 2025-01-20 16:00 | 2025-01-21 06:00 | 11779.06 | 11779.06 | 20.4 | 27.1 | CORR | MATL |  | NT-3000-368691
40300000013 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-TURB-194 | EQ-3000-84774 | 4 | Low |  | REPL | Replacement | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-09 | 2025-01-19 00:00 | 2025-01-20 05:00 | 2025-01-19 00:59 | 2025-01-19 11:59 | 19926.15 | 19926.15 | 22.4 | 22.4 | VIBR | ENVR | X | NT-3000-182289
40300000014 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-889 | EQ-3000-53829 | 3 | Medium | MP-3000-039 | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-08 | 2025-01-22 00:00 | 2025-01-24 09:00 | 2025-01-22 16:23 | 2025-01-24 23:23 | 21809.77 | 27676.72 | 28.8 | 28.8 | NONE
40300000015 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-412 | EQ-3000-78731 | 1 | Very High |  | OVHL | Overhaul | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-06 | 2025-01-12 00:00 | 2025-01-14 23:00 | 2025-01-12 00:00 | 2025-01-15 02:00 | 8507.37 | 8507.37 | 84.3 | 84.3 | OVER | AGE |  | NT-3000-889410