## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000016 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-689 | EQ-3000-76155 | 3 | Medium | MP-3000-048 | TEST | Testing | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-13 | 2025-01-17 00:00 | 2025-01-19 09:00 | 2025-01-17 00:00 | 2025-01-18 15:00 | 4126.3 | 4409.43 | 41.7 | 41.7 | NONE
40300000017 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-TURB-187 | EQ-3000-62235 | 3 | Medium | MP-3000-013 | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-17 | 2025-01-24 00:00 | 2025-01-24 18:00 | 2025-01-24 00:00 | 2025-01-24 19:00 | 14202.76 | 19652.48 | 59.6 | 59.6 | NONE
40300000018 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-173 | EQ-3000-44898 | 3 | Medium | MP-3000-013 | REPR | Repair | CRTD | Created | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-19 | 2025-01-26 00:00 | 2025-01-27 19:00 |  |  | 3256.98 |  | 50.8 |  | NONE
40300000019 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-771 | EQ-3000-13172 | 4 | Low |  | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-19 | 2025-01-24 00:00 | 2025-01-24 23:00 | 2025-01-24 00:00 | 2025-01-25 22:00 | 15767.96 | 16489 | 54 | 54 | WEAR | OPER |  | NT-3000-217830
40300000020 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-348 | EQ-3000-91396 | 1 | Very High |  | INSP | Inspection | DLT | Deleted | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-14 | 2025-01-28 00:00 | 2025-01-29 14:00 |  |  | 8910.15 |  | 96.9 |  | CORR | DSGN | X | NT-3000-875959
40300000021 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-316 | EQ-3000-36712 | 4 | Low |  | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-17 | 2025-01-26 00:00 | 2025-01-27 11:00 | 2025-01-26 00:00 | 2025-01-29 00:00 | 15764.53 | 15764.53 | 119.1 | 119.1 | LEAK | DSGN |  | NT-3000-367865
40300000022 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-161 | EQ-3000-47226 | 3 | Medium |  | INSP | Inspection | PCNF | Partially Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-14 | 2025-01-27 00:00 | 2025-01-28 12:00 | 2025-01-27 15:51 |  | 11891.54 |  | 113.5 |  | VIBR | DSGN |  | NT-3000-213132
40300000023 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-399 | EQ-3000-95119 | 4 | Low | MP-3000-006 | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-16 | 2025-01-20 00:00 | 2025-01-22 02:00 | 2025-01-21 06:46 | 2025-01-24 01:46 | 22644.87 | 22644.87 | 59.2 | 59.2 | NONE
40300000024 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-568 | EQ-3000-83490 | 2 | High | MP-3000-023 | CALI | Calibration | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-18 | 2025-01-19 00:00 | 2025-01-19 07:00 | 2025-01-19 00:00 | 2025-01-20 09:00 | 8672.46 | 10512.64 | 48.4 | 48.4 | NONE
40300000025 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-740 | EQ-3000-49626 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-14 | 2025-01-23 00:00 | 2025-01-24 13:00 | 2025-01-23 06:52 | 2025-01-23 15:52 | 22027.59 | 25194.7 | 107.1 | 131.7 | LEAK | ENVR |  | NT-3000-458388
40300000026 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-772 | EQ-3000-27991 | 3 | Medium | MP-3000-020 | LUBR | Lubrication | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-13 | 2025-01-25 00:00 | 2025-01-27 02:00 | 2025-01-25 00:00 | 2025-01-27 20:00 | 10724.67 | 11626.7 | 69.6 | 109.9 | NONE
40300000027 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-655 | EQ-3000-27271 | 4 | Low |  | LUBR | Lubrication | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-14 | 2025-01-25 00:00 | 2025-01-25 19:00 | 2025-01-25 00:00 | 2025-01-28 04:00 | 21633.4 | 24659.54 | 38.5 | 54 | NONE | OPER |  | NT-3000-432918
40300000028 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-670 | EQ-3000-79856 | 1 | Very High |  | OVHL | Overhaul | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-18 | 2025-01-20 00:00 | 2025-01-21 01:00 | 2025-01-20 07:13 | 2025-01-22 01:13 | 18313.45 | 19202.04 | 92.3 | 108.4 | BLOC | DSGN | X | NT-3000-259338
40300000029 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-209 | EQ-3000-27241 | 5 | Unknown |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-14 | 2025-01-15 00:00 | 2025-01-16 12:00 | 2025-01-15 00:00 | 2025-01-18 07:00 | 15110.84 | 16591.39 | 29.2 | 32.9 | LEAK | MATL | X | NT-3000-626725
40300000030 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-HEAT-580 | EQ-3000-95140 | 3 | Medium |  | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-15 | 2025-01-18 00:00 | 2025-01-20 03:00 | 2025-01-18 00:00 | 2025-01-20 16:00 | 3869.06 | 3876.55 | 24.8 | 24.8 | LEAK | DSGN | X | NT-3000-533108
40300000031 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-860 | EQ-3000-97993 | 3 | Medium |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-14 | 2025-01-27 00:00 | 2025-01-28 04:00 | 2025-01-27 20:29 | 2025-01-28 06:29 | 23214.03 | 29692.91 | 118.3 | 118.3 | NOIS | UNKN |  | NT-3000-548324