## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000032 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-CONV-894 | EQ-3000-15482 | 3 | Medium | MP-3000-035 | REPL | Replacement | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-24 | 2025-02-05 00:00 | 2025-02-07 02:00 |  |  | 10156.69 |  | 112.8 |  | NONE
40300000033 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-211 | EQ-3000-69193 | 1 | Very High |  | TEST | Testing | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-23 | 2025-02-06 00:00 | 2025-02-06 07:00 | 2025-02-06 17:59 | 2025-02-08 02:59 | 24603.85 | 26309.68 | 6.6 | 6.8 | BLOC | ENVR |  | NT-3000-405323
40300000034 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-507 | EQ-3000-49918 | 3 | Medium |  | OVHL | Overhaul | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-26 | 2025-02-09 00:00 | 2025-02-10 14:00 | 2025-02-09 16:02 | 2025-02-12 05:02 | 10850.32 | 11904.9 | 74.3 | 74.3 | LEAK | UNKN |  | NT-3000-970206
40300000035 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-192 | EQ-3000-75622 | 3 | Medium | MP-3000-038 | TEST | Testing | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-20 | 2025-01-23 00:00 | 2025-01-25 23:00 | 2025-01-23 00:00 | 2025-01-23 19:00 | 10632.2 | 10632.2 | 55.2 | 70.6 | NONE
40300000036 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-192 | EQ-3000-42778 | 2 | High |  | REPR | Repair | DLT | Deleted | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-22 | 2025-02-03 00:00 | 2025-02-03 22:00 |  |  | 2734.19 |  | 85.3 |  | ELEC | AGE |  | NT-3000-497073
40300000037 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-489 | EQ-3000-15754 | 4 | Low | MP-3000-004 | OVHL | Overhaul | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-26 | 2025-01-29 00:00 | 2025-01-30 20:00 | 2025-01-29 00:00 | 2025-02-01 02:00 | 4472.04 | 4559.95 | 19.1 | 23.3 | NONE
40300000038 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-847 | EQ-3000-68491 | 3 | Medium | MP-3000-001 | OVHL | Overhaul | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-22 | 2025-02-02 00:00 | 2025-02-03 01:00 | 2025-02-02 00:00 | 2025-02-02 17:00 | 24030.63 | 27990.6 | 2.4 | 2.9 | NONE
40300000039 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-656 | EQ-3000-10753 | 4 | Low | MP-3000-001 | CLEA | Cleaning | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-24 | 2025-02-01 00:00 | 2025-02-02 08:00 | 2025-02-01 13:03 | 2025-02-02 18:03 | 11616.59 | 11616.59 | 54.1 | 59.1 | NONE
40300000040 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-743 | EQ-3000-83079 | 1 | Very High |  | OVHL | Overhaul | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-26 | 2025-02-09 00:00 | 2025-02-10 04:00 | 2025-02-09 00:00 | 2025-02-09 08:00 | 4132.28 | 4455.93 | 79.1 | 79.1 | LEAK | OPER |  | NT-3000-447195
40300000041 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-150 | EQ-3000-24272 | 4 | Low |  | CALI | Calibration | REL | Released | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-23 | 2025-01-26 00:00 | 2025-01-26 22:00 |  |  | 15471.7 |  | 83.6 |  | NONE | OPER | X | NT-3000-137581
40300000042 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-886 | EQ-3000-49229 | 3 | Medium |  | TEST | Testing | CNF | Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-22 | 2025-01-28 00:00 | 2025-01-30 02:00 | 2025-01-28 00:18 | 2025-01-28 10:18 | 21161.09 | 23281.03 | 9.7 | 9.7 | NOIS | OPER | X | NT-3000-652654
40300000043 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-CONV-637 | EQ-3000-37504 | 3 | Medium | MP-3000-006 | REPR | Repair | REL | Released | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-25 | 2025-01-29 00:00 | 2025-01-29 09:00 |  |  | 14498.49 |  | 117.6 |  | NONE
40300000044 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-723 | EQ-3000-51482 | 3 | Medium | MP-3000-012 | CLEA | Cleaning | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-22 | 2025-01-31 00:00 | 2025-02-01 23:00 | 2025-01-31 00:00 | 2025-01-31 18:00 | 13232.79 | 13232.79 | 76.6 | 93.1 | NONE
40300000045 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-298 | EQ-3000-10207 | 3 | Medium |  | LUBR | Lubrication | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-20 | 2025-01-21 00:00 | 2025-01-23 13:00 | 2025-01-21 01:40 | 2025-01-21 18:40 | 20089.33 | 22336.01 | 119.9 | 126.4 | BLOC | AGE |  | NT-3000-111846
40300000046 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-COMP-806 | EQ-3000-46913 | 3 | Medium | MP-3000-044 | CALI | Calibration | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-22 | 2025-02-04 00:00 | 2025-02-04 10:00 | 2025-02-04 00:00 | 2025-02-05 17:00 |  | 14561.42 | 40.2 | 56.7 | NONE