## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000047 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-841 | EQ-3000-84569 | 3 | Medium | MP-3000-031 | REPL | Replacement | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-31 | 2025-02-01 00:00 | 2025-02-02 00:00 | 2025-02-01 18:52 | 2025-02-02 20:52 | 20928.72 | 25669.2 | 110.8 | 128.7 | NONE
40300000048 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-259 | EQ-3000-92208 | 3 | Medium |  | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-30 | 2025-02-13 00:00 | 2025-02-15 22:00 | 2025-02-13 08:42 | 2025-02-15 04:42 | 19707.73 | 20173.93 | 50.8 | 53.1 | LEAK | ENVR | X | NT-3000-682145
40300000049 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-119 | EQ-3000-37297 | 1 | Very High |  | REPR | Repair | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-31 | 2025-02-11 00:00 | 2025-02-12 20:00 | 2025-02-11 00:00 | 2025-02-12 23:00 | 24255.53 | 24402.8 | 35.1 | 37 | LEAK | MATL |  | NT-3000-698717
40300000050 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-498 | EQ-3000-34560 | 3 | Medium |  | REPL | Replacement | REL | Released | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-31 | 2025-02-02 00:00 | 2025-02-03 17:00 |  |  | 17891.08 |  | 34 |  | VIBR | DSGN |  | NT-3000-969749
40300000051 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-TURB-321 | EQ-3000-78825 | 1 | Very High |  | INSP | Inspection | CNF | Confirmed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-29 | 2025-02-01 00:00 | 2025-02-01 16:00 | 2025-02-01 00:00 | 2025-02-03 01:00 |  | 24813.22 | 109.8 | 109.8 | NOIS | ENVR | X | NT-3000-299451
40300000052 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-595 | EQ-3000-78632 | 4 | Low |  | REPR | Repair | CNF | Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-29 | 2025-02-11 00:00 | 2025-02-12 19:00 | 2025-02-11 00:00 | 2025-02-11 20:00 | 20642.39 | 23519.61 | 112.7 | 122.7 | OVER | OPER |  | NT-3000-848344
40300000053 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-218 | EQ-3000-10538 | 4 | Low |  | CLEA | Cleaning | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-01-29 | 2025-01-30 00:00 | 2025-01-30 13:00 | 2025-01-30 03:12 | 2025-01-31 23:12 | 22285.05 | 31137.87 | 14.2 | 19.4 | CORR | AGE |  | NT-3000-436467
40300000054 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-COMP-297 | EQ-3000-47560 | 1 | Very High | MP-3000-008 | CLEA | Cleaning | PCNF | Partially Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-29 | 2025-02-07 00:00 | 2025-02-08 18:00 | 2025-02-07 00:00 |  | 16942.54 |  | 34.2 |  | NONE
40300000055 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-COMP-655 | EQ-3000-55916 | 3 | Medium | MP-3000-011 | OVHL | Overhaul | DLT | Deleted | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-31 | 2025-02-06 00:00 | 2025-02-07 12:00 |  |  | 23610.31 |  | 96.9 |  | NONE
40300000056 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-446 | EQ-3000-80854 | 4 | Low | MP-3000-006 | CLEA | Cleaning | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-30 | 2025-01-31 00:00 | 2025-01-31 18:00 | 2025-01-31 00:00 | 2025-01-31 05:00 | 22630.66 | 23820.79 | 8 | 9.4 | NONE
40300000057 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-821 | EQ-3000-88134 | 3 | Medium | MP-3000-043 | REPL | Replacement | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-01-31 | 2025-02-11 00:00 | 2025-02-13 11:00 |  |  | 8154.8 |  | 98.5 |  | NONE
40300000058 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-681 | EQ-3000-27274 | 2 | High |  | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-01-27 | 2025-02-10 00:00 | 2025-02-12 13:00 | 2025-02-10 18:26 | 2025-02-11 08:26 | 8104.6 | 8245.78 | 78 | 78 | NOIS | DSGN |  | NT-3000-746910
40300000059 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-472 | EQ-3000-61390 | 1 | Very High |  | CLEA | Cleaning | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-01-28 | 2025-02-09 00:00 | 2025-02-10 20:00 | 2025-02-09 18:49 | 2025-02-11 13:49 | 12443.91 | 13090.82 | 9.7 | 9.7 | VIBR | MATL |  | NT-3000-905245
40300000060 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-TURB-718 | EQ-3000-85324 | 3 | Medium | MP-3000-035 | REPR | Repair | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-28 | 2025-02-06 00:00 | 2025-02-06 15:00 | 2025-02-06 09:47 | 2025-02-08 14:47 | 8483.81 | 10185.43 | 78.6 | 78.6 | NONE
40300000061 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-HEAT-523 | EQ-3000-41270 | 3 | Medium | MP-3000-045 | OVHL | Overhaul | PCNF | Partially Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-01-31 | 2025-02-04 00:00 | 2025-02-07 00:00 | 2025-02-04 12:11 |  | 24360.35 |  | 47.3 |  | NONE
40300000062 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-680 | EQ-3000-54852 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-01-31 | 2025-02-12 00:00 | 2025-02-13 08:00 | 2025-02-12 13:43 | 2025-02-13 13:43 | 18614.49 | 18614.49 | 86 | 101.3 | NOIS | AGE |  | NT-3000-682051