## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000125 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-242 | EQ-3000-86962 | 3 | Medium | MP-3000-022 | LUBR | Lubrication | REL | Released | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-07 | 2025-03-09 00:00 | 2025-03-09 20:00 |  |  | 7929.16 |  | 118.6 |  | NONE
40300000126 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-106 | EQ-3000-63668 | 4 | Low |  | CLEA | Cleaning | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-08 | 2025-03-13 00:00 | 2025-03-15 07:00 | 2025-03-13 17:24 | 2025-03-14 17:24 | 17901.05 | 23580.6 | 91.1 | 91.1 | OVER | OPER |  | NT-3000-680771
40300000127 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-CONV-143 | EQ-3000-49582 | 1 | Very High | MP-3000-020 | CLEA | Cleaning | CNF | Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-09 | 2025-03-19 00:00 | 2025-03-20 16:00 | 2025-03-19 00:00 | 2025-03-21 17:00 | 6000.75 | 6144.4 | 95.4 | 95.4 | NONE
40300000128 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-769 | EQ-3000-97282 | 1 | Very High |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-05 | 2025-03-12 00:00 | 2025-03-13 00:00 | 2025-03-12 01:14 | 2025-03-14 17:14 | 1196.84 | 1196.84 | 92.2 | 113.2 | NOIS | AGE | X | NT-3000-693047
40300000129 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-989 | EQ-3000-43804 | 2 | High |  | REPL | Replacement | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-08 | 2025-03-19 00:00 | 2025-03-21 14:00 | 2025-03-19 16:25 | 2025-03-20 09:25 | 13056.88 | 13056.88 | 69.9 | 69.9 | CORR | OPER |  | NT-3000-583439
40300000130 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-465 | EQ-3000-31405 | 2 | High |  | REPL | Replacement | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-03 | 2025-03-08 00:00 | 2025-03-10 00:00 | 2025-03-08 06:29 | 2025-03-10 13:29 | 1693.52 | 1880.49 | 36.4 | 36.4 | VIBR | ENVR |  | NT-3000-901834
40300000129 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-713 | EQ-3000-31906 | 4 | Low | MP-3000-038 | CALI | Calibration | CNF | Confirmed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-07 | 2025-03-13 00:00 | 2025-03-14 18:00 | 2025-03-13 06:07 | 2025-03-14 22:07 | 17293.37 | 19534.58 | 83.2 | 83.2 | NONE
40300000132 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-240 | EQ-3000-77917 | 3 | Medium | MP-3000-033 | REPL | Replacement | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-05 | 2025-03-11 00:00 | 2025-03-13 16:00 | 2025-03-11 13:44 | 2025-03-13 19:44 | 23062.23 | 23062.23 | 21.2 | 25.7 | NONE
40300000133 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-728 | EQ-3000-78898 | 2 | High |  | TEST | Testing | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-09 | 2025-03-18 00:00 | 2025-03-21 00:00 | 2025-03-18 22:27 | 2025-03-19 14:27 | 11782.04 | 12580.43 | 11 | 12.2 | OVER | AGE |  | NT-3000-245766
40300000134 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-711 | EQ-3000-78566 | 3 | Medium | MP-3000-045 | INSP | Inspection | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-09 | 2025-03-15 00:00 | 2025-03-16 00:00 | 2025-03-15 01:14 | 2025-03-16 17:14 | 18739.28 | 20491 | 16 | 16 | NONE
40300000135 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-228 | EQ-3000-37504 | 4 | Low |  | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-04 | 2025-03-06 00:00 | 2025-03-08 08:00 | 2025-03-06 10:10 | 2025-03-07 02:10 | 960.76 | 1001.3 | 59.1 | 67 | BLOC | AGE |  | NT-3000-591868
40300000136 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-359 | EQ-3000-15672 | 4 | Low | MP-3000-013 | REPR | Repair | REL | Released | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-03 | 2025-03-08 00:00 | 2025-03-08 03:00 |  |  | 19668.08 |  | 110.6 |  | NONE
40300000137 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-192 | EQ-3000-29078 | 3 | Medium | MP-3000-040 | REPL | Replacement | REL | Released | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-09 | 2025-03-21 00:00 | 2025-03-22 13:00 |  |  | 9128.98 |  | 102.9 |  | NONE
40300000138 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-939 | EQ-3000-85777 | 4 | Low | MP-3000-001 | LUBR | Lubrication | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-09 | 2025-03-10 00:00 | 2025-03-12 21:00 | 2025-03-10 00:00 | 2025-03-11 05:00 | 24124.46 | 24124.46 | 22.3 | 31.2 | NONE
40300000139 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-COMP-616 | EQ-3000-72221 | 2 | High | MP-3000-014 | REPR | Repair | CLSD | Closed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-05 | 2025-03-17 00:00 | 2025-03-18 01:00 | 2025-03-17 20:34 | 2025-03-20 06:34 | 4930.79 | 5689.53 | 43.9 | 51.1 | NONE