## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000140 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-215 | EQ-3000-51193 | 2 | High | MP-3000-047 | OVHL | Overhaul | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-10 | 2025-03-18 00:00 | 2025-03-18 16:00 | 2025-03-18 00:00 | 2025-03-20 20:00 | 12647.49 | 12647.49 | 44.6 | 46.2 | NONE
40300000141 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-TURB-605 | EQ-3000-25167 | 3 | Medium | MP-3000-027 | CALI | Calibration | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-13 | 2025-03-18 00:00 | 2025-03-20 12:00 | 2025-03-18 00:00 | 2025-03-21 06:00 | 17332.64 | 20126.34 | 101.2 | 115.4 | NONE
40300000142 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-977 | EQ-3000-19123 | 4 | Low |  | OVHL | Overhaul | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-03-16 | 2025-03-29 00:00 | 2025-03-31 14:00 | 2025-03-29 09:47 | 2025-03-31 10:47 | 813.25 | 813.25 | 81.6 | 99.9 | VIBR | DSGN | X | NT-3000-225008
40300000143 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-504 | EQ-3000-62510 | 1 | Very High |  | REPR | Repair | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-15 | 2025-03-25 00:00 | 2025-03-25 15:00 | 2025-03-25 14:38 | 2025-03-26 13:38 | 9410.89 | 10569.13 | 25.5 | 30.7 | WEAR | ENVR |  | NT-3000-344181
40300000144 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-842 | EQ-3000-75419 | 2 | High |  | REPL | Replacement | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-12 | 2025-03-25 00:00 | 2025-03-26 12:00 | 2025-03-25 07:38 | 2025-03-27 12:38 | 12157.74 | 14689.4 | 73.2 | 73.5 | BLOC | DSGN |  | NT-3000-213284
40300000145 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-356 | EQ-3000-74138 | 2 | High | MP-3000-002 | REPR | Repair | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-13 | 2025-03-17 00:00 | 2025-03-17 19:00 | 2025-03-17 21:26 | 2025-03-18 02:26 | 18576.06 | 18576.06 | 100 | 100 | NONE
40300000146 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-HEAT-795 | EQ-3000-52854 | 4 | Low | MP-3000-030 | REPR | Repair | REL | Released | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-11 | 2025-03-16 00:00 | 2025-03-16 14:00 |  |  | 16696.47 |  | 63.4 |  | NONE
40300000147 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-602 | EQ-3000-76164 | 2 | High |  | INSP | Inspection | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-12 | 2025-03-21 00:00 | 2025-03-22 21:00 | 2025-03-21 00:00 | 2025-03-23 23:00 | 23838.22 | 26236.68 | 5.7 | 6.9 | BLOC | AGE | X | NT-3000-564053
40300000148 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-136 | EQ-3000-14306 | 4 | Low | MP-3000-049 | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-11 | 2025-03-20 00:00 | 2025-03-21 16:00 | 2025-03-20 03:48 | 2025-03-21 02:48 | 11051.69 | 11051.69 | 38.9 | 47.2 | NONE
40300000149 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-801 | EQ-3000-80699 | 2 | High | MP-3000-025 | OVHL | Overhaul | REL | Released | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-14 | 2025-03-22 00:00 | 2025-03-24 14:00 |  |  | 12913.78 |  | 48.2 |  | NONE
40300000150 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-428 | EQ-3000-18050 | 3 | Medium | MP-3000-041 | REPL | Replacement | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-10 | 2025-03-20 00:00 | 2025-03-20 07:00 | 2025-03-20 10:50 | 2025-03-21 04:50 |  | 11266.17 | 89.6 | 89.6 | NONE
40300000151 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-538 | EQ-3000-55238 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-03-12 | 2025-03-21 22:00 | 2025-03-20 22:00 | 2025-03-19 00:00 | 2025-03-19 09:00 | 6566.54 | 6566.54 | 78.5 | 90.8 | VIBR | UNKN |  | NT-3000-453993
40300000152 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-120 | EQ-3000-80571 | 4 | Low |  | TEST | Testing | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-12 | 2025-03-13 00:00 | 2025-03-15 12:00 | 2025-03-13 10:35 | 2025-03-15 18:35 | 7032.16 | 7466.44 | 84.1 | 86.2 | LEAK | MATL |  | NT-3000-700350
40300000153 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-927 | EQ-3000-74010 | 3 | Medium |  | CLEA | Cleaning | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-10 | 2025-03-22 00:00 | 2025-03-23 04:00 | 2025-03-22 07:56 | 2025-03-24 04:56 | 12817.83 | 16147.02 | 92.3 | 92.3 | ELEC | OPER |  | NT-3000-311559
40300000154 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-750 | EQ-3000-19872 | 2 | High |  | CALI | Calibration | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-03-16 | 2025-03-30 00:00 | 2025-04-01 22:00 | 2025-03-30 15:03 | 2025-03-31 20:03 | 6996.3 | 8202.48 | 37.1 | 42.1 | BLOC | OPER |  | NT-3000-720615
40300000155 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-379 | EQ-3000-18817 | 3 | Medium |  | CLEA | Cleaning | PCNF | Partially Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-14 | 2025-03-27 00:00 | 2025-03-29 21:00 | 2025-03-27 06:51 |  | 10964.09 |  | 43 |  | VIBR | UNKN |  | NT-3000-553939