## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000187 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-TURB-676 | EQ-3000-88687 | 2 | High |  | OVHL | Overhaul | CLSD | Closed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-04-03 | 2025-04-05 00:00 | 2025-04-07 08:00 | 2025-04-05 00:22 | 2025-04-07 01:22 | 11135.6 | 11465.52 | 52.3 | 61.7 | LEAK | ENVR | X | NT-3000-779068
40300000188 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-COMP-607 | EQ-3000-79111 | 2 | High | MP-3000-031 | REPR | Repair | REL | Released | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-04-05 | 2025-04-16 00:00 | 2025-04-18 21:00 |  |  | 7622.22 |  | 53.6 |  | NONE
40300000189 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-800 | EQ-3000-49375 | 2 | High |  | CALI | Calibration | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-04-06 | 2025-04-10 00:00 | 2025-04-12 20:00 | 2025-04-10 08:25 | 2025-04-12 16:25 | 14429.12 | 16555.38 | 67 | 69 | LEAK | ENVR | X | NT-3000-199074
40300000190 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-776 | EQ-3000-84511 | 1 | Very High | MP-3000-030 | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-04-06 | 2025-04-11 00:00 | 2025-04-12 23:00 | 2025-04-11 00:00 | 2025-04-12 10:00 | 19331.85 | 22233.15 | 3.9 | 5.2 | NONE
40300000191 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-146 | EQ-3000-20917 | 3 | Medium |  | CLEA | Cleaning | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-04-03 | 2025-04-15 00:00 | 2025-04-16 16:00 | 2025-04-15 20:01 | 2025-04-17 14:01 | 19055.18 | 22760.7 | 55.1 | 69.7 | CORR | MATL |  | NT-3000-294078
40300000192 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-864 | EQ-3000-89174 | 4 | Low | MP-3000-031 | INSP | Inspection | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-04-02 | 2025-04-16 00:00 | 2025-04-16 15:00 | 2025-04-17 04:14 | 2025-04-19 13:14 | 643.25 | 721.55 | 15.8 | 16.7 | NONE
40300000193 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-843 | EQ-3000-73795 | 2 | High | MP-3000-002 | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-04-02 | 2025-04-12 00:00 | 2025-04-14 00:00 | 2025-04-12 00:00 | 2025-04-14 04:00 | 2647.06 | 2692.12 | 17.9 | 21.3 | NONE
40300000194 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-314 | EQ-3000-73060 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-04-05 | 2025-04-08 00:00 | 2025-04-09 08:00 | 2025-04-08 05:54 | 2025-04-10 14:54 | 2609.29 | 3115.04 | 92.8 | 113.9 | OVER | DSGN | X | NT-3000-259826