## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000094 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-HEAT-719 | EQ-1000-66387 | 4 | Low |  | LUBR | Lubrication | DLT | Deleted | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-17 | 2025-03-02 00:00 | 2025-03-02 16:00 |  |  | 11036.71 |  | 106.8 |  | BLOC | MATL | X | NT-1000-865054
40100000093 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-PUMP-420 | EQ-1000-65936 | 3 | Medium |  | OVHL | Overhaul | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-19 | 2025-03-02 00:00 | 2025-03-03 10:00 | 2025-03-02 00:00 | 2025-03-04 01:00 | 17327.12 | 17327.12 | 58 | 58 | VIBR | AGE | X | NT-1000-951201
40100000096 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-669 | EQ-1000-17861 | 4 | Low | MP-1000-047 | TEST | Testing | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-21 | 2025-03-02 00:00 | 2025-03-03 20:00 | 2025-03-02 04:16 | 2025-03-02 21:16 | 9163.15 | 9163.15 | 80.5 | 80.5 | NONE
40100000097 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-419 | EQ-1000-56090 | 3 | Medium | MP-1000-036 | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-17 | 2025-02-27 00:00 | 2025-03-01 18:00 | 2025-02-27 07:39 | 2025-02-28 12:39 | 16590.04 | 16875.87 | 28.5 | 38.8 | NONE
40100000098 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-TURB-687 | EQ-1000-39643 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-23 | 2025-03-02 00:00 | 2025-03-02 05:00 | 2025-03-02 00:00 | 2025-03-05 07:00 | 1209.35 | 1385.6 | 34.2 | 40.3 | CORR | MATL | X | NT-1000-693830
40100000099 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-CONV-171 | EQ-1000-28595 | 2 | High | MP-1000-022 | REPR | Repair | PCNF | Partially Confirmed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-22 | 2025-03-05 00:00 | 2025-03-05 05:00 | 2025-03-05 12:56 |  | 18779.74 |  | 27.4 |  | NONE
40100000100 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-838 | EQ-1000-52517 | 3 | Medium | MP-1000-018 | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-23 | 2025-03-05 00:00 | 2025-03-05 12:00 | 2025-03-05 00:00 | 2025-03-05 08:00 | 4356.54 | 4356.54 | 74.9 | 74.9 | NONE
40100000101 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-721 | EQ-1000-67939 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-20 | 2025-02-25 00:00 | 2025-02-26 05:00 | 2025-02-25 04:18 | 2025-02-27 23:18 | 8956.73 | 10275.45 | 15.1 | 16.9 | NOIS | ENVR |  | NT-1000-514463
40100000102 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-HEAT-156 | EQ-1000-11007 | 1 | Very High |  | CALI | Calibration | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-18 | 2025-02-23 00:00 | 2025-02-24 05:00 | 2025-02-23 00:00 | 2025-02-23 19:00 | 7591.45 | 7591.45 | 16.2 | 18.3 | NOIS | UNKN | X | NT-1000-658453
40100000103 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-612 | EQ-1000-83233 | 2 | High |  | TEST | Testing | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-23 | 2025-03-06 00:00 | 2025-03-07 23:00 | 2025-03-06 00:00 | 2025-03-06 11:00 | 21613.23 | 21613.23 | 7 | 7.2 | LEAK | DSGN |  | NT-1000-701253
40100000104 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-826 | EQ-1000-93904 | 2 | High | MP-1000-040 | TEST | Testing | PCNF | Partially Confirmed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-20 | 2025-02-25 00:00 | 2025-02-25 16:00 | 2025-02-25 04:55 |  | 1010.99 |  | 40.3 |  | NONE
40100000105 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-547 | EQ-1000-23875 | 3 | Medium | MP-1000-022 | REPR | Repair | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-18 | 2025-02-25 00:00 | 2025-02-27 05:00 | 2025-02-25 00:00 | 2025-02-27 21:00 | 10196.28 | 13339.42 | 38.6 | 38.6 | NONE
40100000106 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-748 | EQ-1000-24945 | 2 | High | MP-1000-010 | REPL | Replacement | CRTD | Created | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-21 | 2025-03-02 00:00 | 2025-03-03 02:00 |  |  | 9101.94 |  | 115.1 |  | NONE
40100000107 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-362 | EQ-1000-35856 | 3 | Medium | MP-1000-049 | REPR | Repair | PCNF | Partially Confirmed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-02-18 | 2025-02-28 00:00 | 2025-02-28 21:00 | 2025-02-28 00:00 |  | 4840.08 |  | 93.2 |  | NONE
40100000108 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-HEAT-758 | EQ-1000-93269 | 3 | Medium |  | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-02-21 | 2025-02-27 00:00 | 2025-02-28 18:00 | 2025-02-27 00:00 | 2025-02-27 21:00 | 2173.01 | 2173.01 | 54.2 | 59.2 | CORR | MATL |  | NT-1000-425486