## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000016 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-690 | EQ-1000-71953 | 3 | Medium | MP-1000-027 | LUBR | Lubrication | CNF | Confirmed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-14 | 2025-01-27 00:00 | 2025-01-29 14:00 | 2025-01-27 04:52 | 2025-01-29 10:52 | 2810.98 | 3382.83 | 79.8 | 82.6 | NONE
40100000017 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-162 | EQ-1000-62772 | 3 | Medium | MP-1000-018 | LUBR | Lubrication | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-18 | 2025-01-24 00:00 | 2025-01-24 15:00 | 2025-01-24 06:01 | 2025-01-25 15:01 | 5160.12 | 6317.61 | 54.9 | 61.4 | NONE
40100000018 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-PUMP-553 | EQ-1000-82132 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-13 | 2025-01-14 00:00 | 2025-01-16 23:00 | 2025-01-14 00:31 | 2025-01-14 03:31 | 23195.99 | 23195.99 | 102.1 | 109.1 | OVER | DSGN |  | NT-1000-161483
40100000019 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-COMP-488 | EQ-1000-10282 | 2 | High |  | TEST | Testing | TECO | Technically Complete | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-16 | 2025-01-21 00:00 | 2025-01-23 12:00 | 2025-01-21 00:00 | 2025-01-22 14:00 | 17566.49 | 17566.49 | 88.2 | 105.7 | NONE | UNKN | X | NT-1000-411120
40100000020 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-159 | EQ-1000-85914 | 3 | Medium | MP-1000-034 | REPL | Replacement | PCNF | Partially Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-18 | 2025-01-27 00:00 | 2025-01-27 09:00 | 2025-01-27 09:19 |  | 1900.55 |  | 70.9 |  | NONE
40100000021 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-182 | EQ-1000-34356 | 2 | High | MP-1000-039 | TEST | Testing | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-13 | 2025-01-23 00:00 | 2025-01-23 10:00 | 2025-01-23 01:58 | 2025-01-24 09:58 | 3437.22 | 4144.53 | 107.1 | 116.2 | NONE
40100000022 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-CONV-773 | EQ-1000-86503 | 2 | High |  | CALI | Calibration | REL | Released | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-17 | 2025-01-26 00:00 | 2025-01-27 18:00 |  |  | 5504.35 |  | 86.5 |  | WEAR | MATL | X | NT-1000-579434
40100000023 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-869 | EQ-1000-19508 | 3 | Medium | MP-1000-005 | LUBR | Lubrication | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-13 | 2025-01-21 00:00 | 2025-01-21 14:00 | 2025-01-21 00:00 | 2025-01-21 11:00 | 12894.18 | 13562.46 | 17.6 | 17.6 | NONE
40100000024 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-261 | EQ-1000-67433 | 4 | Low |  | INSP | Inspection | CNF | Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-19 | 2025-01-28 00:00 | 2025-01-29 16:00 | 2025-01-28 00:00 | 2025-01-31 08:00 | 16862.65 | 21633.56 | 67.4 | 73.1 | VIBR | OPER |  | NT-1000-385577
40100000025 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-719 | EQ-1000-37607 | 4 | Low |  | CALI | Calibration | DLT | Deleted | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-18 | 2025-01-24 00:00 | 2025-01-25 04:00 |  |  | 12882.52 |  | 31.6 |  | LEAK | AGE |  | NT-1000-103717
40100000026 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-889 | EQ-1000-27146 | 3 | Medium | MP-1000-045 | TEST | Testing | CNF | Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-18 | 2025-01-23 00:00 | 2025-01-23 22:00 | 2025-01-23 00:21 | 2025-01-25 10:21 | 14242.22 | 19504.53 | 15.2 | 15.4 | NONE
40100000027 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-696 | EQ-1000-82420 | 3 | Medium | MP-1000-003 | INSP | Inspection | DLT | Deleted | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-14 | 2025-01-21 00:00 | 2025-01-21 18:00 |  |  | 8052.33 |  | 108.1 |  | NONE
40100000028 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-782 | EQ-1000-23473 | 3 | Medium | MP-1000-027 | LUBR | Lubrication | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-15 | 2025-01-28 00:00 | 2025-01-30 06:00 | 2025-01-28 01:48 | 2025-01-28 22:48 | 21682.84 | 24255.61 | 117.2 | 117.2 | NONE
40100000029 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-901 | EQ-1000-63964 | 3 | Medium |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-19 | 2025-01-30 00:00 | 2025-01-31 09:00 | 2025-01-30 00:00 | 2025-01-31 12:00 | 19790.68 | 20018.95 | 14.8 | 14.8 | LEAK | DSGN |  | NT-1000-420015
40100000030 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-328 | EQ-1000-13101 | 1 | Very High | MP-1000-042 | CALI | Calibration | TECO | Technically Complete | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-01-18 | 2025-01-22 00:00 | 2025-01-24 05:00 | 2025-01-22 05:32 | 2025-01-24 01:32 | 21676.65 | 21676.65 | 116.1 | 123.5 | NONE
40100000031 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-439 | EQ-1000-13617 | 2 | High | MP-1000-021 | CALI | Calibration | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-01-13 | 2025-01-18 00:00 | 2025-01-19 00:00 | 2025-01-18 03:43 | 2025-01-21 07:43 | 1437.3 | 1437.3 | 72.4 | 72.4 | NONE