## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000125 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-145 | EQ-1000-56176 | 1 | Very High |  | CLEA | Cleaning | REL | Released | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-07 | 2025-03-15 00:00 | 2025-03-14 00:00 |  |  | 24530.07 |  | 58.5 |  | OVER | OPER |  | NT-1000-407696
40100000126 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-COMP-144 | EQ-1000-36144 | 2 | High |  | TEST | Testing | CLSD | Closed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-03 | 2025-03-09 00:00 | 2025-03-10 17:00 | 2025-03-09 00:17 | 2025-03-11 19:17 | 24733.51 | 27833.95 | 66.1 | 66.1 | CORR | AGE | X | NT-1000-474314
40100000127 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-PUMP-986 | EQ-1000-95948 | 3 | Medium | MP-1000-025 | TEST | Testing | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-05 | 2025-03-10 00:00 | 2025-03-10 17:00 | 2025-03-10 00:00 | 2025-03-12 01:00 | 22292.42 | 22292.42 | 89.7 | 97.2 | NONE
40100000128 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-808 | EQ-1000-75211 | 2 | High | MP-1000-012 | REPR | Repair | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-05 | 2025-03-18 00:00 | 2025-03-20 20:00 | 2025-03-18 00:32 | 2025-03-19 12:32 | 18313.49 | 21521.41 | 11.3 | 12.4 | NONE
40100000129 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-205 | EQ-1000-20494 | 4 | Low | MP-1000-023 | CLEA | Cleaning | CNF | Confirmed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-05 | 2025-03-16 00:00 | 2025-03-17 15:00 | 2025-03-16 00:00 | 2025-03-17 17:00 | 15264.23 | 15264.23 | 52.3 | 60.6 | NONE
40100000130 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-729 | EQ-1000-67008 | 2 | High |  | TEST | Testing | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-05 | 2025-03-16 00:00 | 2025-03-16 09:00 | 2025-03-16 06:12 | 2025-03-16 17:12 | 9401.12 | 11095.03 | 96.5 | 96.5 | OVER | AGE |  | NT-1000-136489
40100000131 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-168 | EQ-1000-40932 | 2 | High |  | TEST | Testing | TECO | Technically Complete | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-09 | 2025-03-20 00:00 | 2025-03-22 00:00 | 2025-03-20 06:18 | 2025-03-22 06:18 | 23761.94 | 23761.94 | 5.8 | 5.8 | OVER | UNKN |  | NT-1000-565504
40100000132 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-PUMP-687 | EQ-1000-28047 | 2 | High |  | CALI | Calibration | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-07 | 2025-03-13 00:00 | 2025-03-15 04:00 | 2025-03-13 00:05 | 2025-03-14 18:05 | 6615.49 | 6849.3 | 15.4 | 18.5 | OVER | DSGN | X | NT-1000-374492
40100000133 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-820 | EQ-1000-68493 | 4 | Low | MP-1000-046 | LUBR | Lubrication | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-04 | 2025-03-14 00:00 | 2025-03-15 14:00 | 2025-03-14 00:00 | 2025-03-16 16:00 | 3504.62 | 3504.62 | 102.6 | 118.2 | NONE
40100000134 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-783 | EQ-1000-55537 | 4 | Low |  | CALI | Calibration | CLSD | Closed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-08 | 2025-03-10 00:00 | 2025-03-13 00:00 | 2025-03-10 07:29 | 2025-03-13 06:29 | 22337.63 | 22337.63 | 102.5 | 102.5 | OVER | MATL |  | NT-1000-930541
40100000135 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-342 | EQ-1000-74752 | 3 | Medium | MP-1000-006 | REPL | Replacement | CRTD | Created | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-03 | 2025-03-09 00:00 | 2025-03-12 00:00 |  |  | 11951.44 |  | 118 |  | NONE
40100000136 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-CONV-834 | EQ-1000-72739 | 5 | Unknown | MP-1000-030 | REPR | Repair | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-07 | 2025-03-14 00:00 | 2025-03-16 06:00 | 2025-03-14 06:13 | 2025-03-17 09:13 | 3570.51 | 3570.51 | 39.4 | 39.4 | NONE
40100000137 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-999 | EQ-1000-82260 | 1 | Very High | MP-1000-034 | TEST | Testing | CNF | Confirmed | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-08 | 2025-03-18 00:00 | 2025-03-19 01:00 | 2025-03-18 00:00 | 2025-03-18 18:00 | 12820.16 | 14673.67 | 104.4 | 129.9 | NONE
40100000138 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-COMP-265 | EQ-1000-52291 | 3 | Medium | MP-1000-036 | CALI | Calibration | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-08 | 2025-03-12 00:00 | 2025-03-13 22:00 | 2025-03-12 00:00 | 2025-03-14 20:00 | 21225.38 | 21225.38 | 31.6 | 31.6 | NONE
40100000139 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-729 |  | 4 | Low |  | OVHL | Overhaul | PCNF | Partially Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-03 | 2025-03-12 00:00 | 2025-03-12 23:00 | 2025-03-12 13:58 |  | 4694.42 |  | 75.7 |  | ELEC | ENVR |  | NT-1000-147670