## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40100000171 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-COMP-168 | EQ-1000-23224 | 3 | Medium | MP-1000-035 | INSP | Inspection | CNF | Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-28 | 2025-03-29 00:00 | 2025-03-31 11:00 | 2025-03-29 00:00 | 2025-04-01 06:00 | 6495.99 | 7610.83 | 7.2 | 7.2 | NONE
40100000172 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-COMP-615 | EQ-1000-47914 | 4 | Low |  | REPL | Replacement | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-25 | 2025-04-08 00:00 | 2025-04-09 18:00 | 2025-04-08 00:00 | 2025-04-11 03:00 | 6304.15 | 6833.5 | 105.4 | 133.5 | NONE | OPER |  | NT-1000-683761
40100000173 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-HEAT-852 | EQ-1000-32955 | 4 | Low | MP-1000-025 | CLEA | Cleaning | CNF | Confirmed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-29 | 2025-04-09 00:00 | 2025-04-11 08:00 | 2025-04-09 00:00 | 2025-04-12 01:00 | 1648.66 | 1648.66 | 42.6 | 51.7 | NONE
40100000174 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-CONV-518 | EQ-1000-29558 | 3 | Medium | MP-1000-010 | CLEA | Cleaning | CNF | Confirmed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-26 | 2025-04-02 00:00 | 2025-04-03 01:00 | 2025-04-02 00:48 | 2025-04-04 22:48 | 6403.72 | 6403.72 | 28.6 | 33.9 | NONE
40100000175 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-HEAT-522 | EQ-1000-64592 | 4 | Low |  | LUBR | Lubrication | CNF | Confirmed | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-28 | 2025-04-06 00:00 | 2025-04-06 19:00 | 2025-04-06 00:00 | 2025-04-08 03:00 | 6747.39 | 7254.49 | 41 | 41 | VIBR | DSGN | X | NT-1000-154040
40100000176 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-TURB-486 | EQ-1000-98299 | 1 | Very High | MP-1000-014 | LUBR | Lubrication | CNF | Confirmed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-28 | 2025-04-07 00:00 | 2025-04-07 07:00 | 2025-04-07 07:40 | 2025-04-07 18:40 | 20213.94 | 24601.31 | 71.3 | 77.7 | NONE
40100000177 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-410 | EQ-1000-12009 | 3 | Medium |  | LUBR | Lubrication | CLSD | Closed | ELEC-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-25 | 2025-03-29 00:00 | 2025-03-29 17:00 | 2025-03-29 00:00 | 2025-03-31 15:00 | 17542.84 | 19083.55 | 85 | 101.4 | BLOC | OPER |  | NT-1000-588899
40100000178 | PM04 | Predictive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-764 | EQ-1000-57088 | 4 | Low | MP-1000-049 | CLEA | Cleaning | TECO | Technically Complete | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-26 | 2025-03-31 00:00 | 2025-04-02 00:00 | 2025-03-31 00:16 | 2025-04-02 19:16 | 11917.1 | 11917.1 | 96.7 | 128.8 | NONE
40100000179 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-TURB-420 | EQ-1000-64254 | 3 | Medium |  | INSP | Inspection | CLSD | Closed | ELEC-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-24 | 2025-04-03 00:00 | 2025-04-04 06:00 | 2025-04-03 00:00 | 2025-04-03 20:00 | 6888.97 | 6888.97 | 112.3 | 112.3 | BLOC | MATL |  | NT-1000-498290
40100000180 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-HEAT-953 | EQ-1000-42208 | 3 | Medium | MP-1000-011 | CLEA | Cleaning | CNF | Confirmed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-27 | 2025-04-05 00:00 | 2025-04-06 21:00 | 2025-04-05 04:45 | 2025-04-06 14:45 | 24179.45 | 24179.45 | 77.7 | 77.7 | NONE
40100000181 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-243 | EQ-1000-81636 | 5 | Unknown | MP-1000-043 | INSP | Inspection | DLT | Deleted | MECH-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-27 | 2025-03-30 00:00 | 2025-04-01 23:00 |  |  | 13336.64 |  | 101 |  | NONE
40100000182 | PM02 | Corrective Maintenance | 1000 | Plant A - Houston | HOU-CONV-240 | EQ-1000-92667 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | MECH-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-25 | 2025-03-27 00:00 | 2025-03-27 21:00 | 2025-03-27 05:54 | 2025-03-27 08:54 | 12890.46 | 12890.46 | 46 | 47.8 | NOIS | UNKN |  | NT-1000-112426
40100000183 | PM03 | Condition-Based Maintenance | 1000 | Plant A - Houston | HOU-PUMP-642 | EQ-1000-46010 | 2 | High | MP-1000-007 | TEST | Testing | DLT | Deleted | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-28 | 2025-04-02 00:00 | 2025-04-02 04:00 |  |  | 20251.11 |  | 109.4 |  | NONE
40100000184 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-COMP-296 | EQ-1000-91235 | 4 | Low | MP-1000-016 | TEST | Testing | TECO | Technically Complete | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-28 | 2025-04-02 00:00 | 2025-04-03 23:00 | 2025-04-02 04:02 | 2025-04-03 16:02 | 2435.97 | 2541.63 | 115.2 | 177.5 | NONE
40100000185 | PM01 | Preventive Maintenance | 1000 | Plant A - Houston | HOU-TURB-800 | EQ-1000-20566 | 2 | High | MP-1000-001 | TEST | Testing | CNF | Confirmed | INST-H1 | PLN-H01 | CC-HOU-MNT | 2025-03-29 | 2025-04-13 06:00 | 2025-04-12 06:00 | 2025-04-12 03:19 | 2025-04-12 16:19 | 9791.97 | 9791.97 | 67.2 | 67.2 | NONE
40100000186 | PM05 | Emergency Maintenance | 1000 | Plant A - Houston | HOU-PUMP-611 | EQ-1000-66873 | 4 | Low |  | REPR | Repair | CLSD | Closed | INST-H1 | PLN-H02 | CC-HOU-MNT | 2025-03-29 | 2025-04-11 00:00 | 2025-04-12 20:00 | 2025-04-11 00:00 | 2025-04-14 02:00 | 22422.38 | 27200.04 | 110.5 | 110.5 | WEAR | OPER | X | NT-1000-384263