## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000063 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-343 | EQ-2000-55457 | 3 | Medium | MP-2000-005 | REPL | Replacement | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-05 | 2025-02-08 00:00 | 2025-02-08 13:00 | 2025-02-08 00:12 |  | 11442.43 |  | 33.3 |  | NONE
40200000064 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-837 | EQ-2000-10167 | 3 | Medium |  | TEST | Testing | REL | Released | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-03 | 2025-02-10 00:00 | 2025-02-12 10:00 |  |  | 24242.99 |  | 106.4 |  | NOIS | DSGN |  | NT-2000-969067
40200000065 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-907 |  | 3 | Medium | MP-2000-002 | OVHL | Overhaul | DLT | Deleted | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-08 | 2025-02-21 00:00 | 2025-02-22 06:00 |  |  | 11556.54 |  | 96.3 |  | NONE
40200000066 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-175 |  | 4 | Low |  | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-04 | 2025-02-11 00:00 | 2025-02-11 22:00 | 2025-02-11 00:45 | 2025-02-11 11:45 | 8779.79 | 8779.79 | 118.3 | 127.1 | NOIS | UNKN |  | NT-2000-736818
40200000067 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-260 | EQ-2000-17019 | 4 | Low | MP-2000-017 | TEST | Testing | CNF | Confirmed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-03 | 2025-02-09 00:00 | 2025-02-10 04:00 | 2025-02-09 03:15 | 2025-02-10 05:15 | 17581.32 | 18898.96 | 87.2 | 87.2 | NONE
40200000068 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-TURB-343 | EQ-2000-22571 | 4 | Low |  | OVHL | Overhaul | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-03 | 2025-02-10 00:00 | 2025-02-13 00:00 | 2025-02-10 00:00 | 2025-02-12 16:00 | 1835.37 | 1835.37 | 2.5 | 2.5 | VIBR | MATL |  | NT-2000-309374
40200000069 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-126 | EQ-2000-37125 | 2 | High | MP-2000-032 | CLEA | Cleaning | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-04 | 2025-02-15 00:00 | 2025-02-16 15:00 | 2025-02-15 05:22 | 2025-02-15 17:22 | 21172.34 | 21932.88 | 38.4 | 38.4 | NONE
40200000070 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-757 | EQ-2000-81319 | 3 | Medium |  | TEST | Testing | PCNF | Partially Confirmed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-06 | 2025-02-09 00:00 | 2025-02-11 01:00 | 2025-02-09 07:04 |  | 9550.34 |  | 54.6 |  | CORR | DSGN |  | NT-2000-691655
40200000071 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-254 | EQ-2000-97486 | 2 | High | MP-2000-025 | TEST | Testing | CRTD | Created | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-03 | 2025-02-05 00:00 | 2025-02-06 22:00 |  |  | 24282.29 |  | 71.6 |  | NONE
40200000072 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-803 |  | 3 | Medium | MP-2000-037 | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-07 | 2025-02-11 00:00 | 2025-02-13 14:00 | 2025-02-11 02:28 | 2025-02-12 18:28 | 10172.71 | 10172.71 | 102.8 | 102.8 | NONE
40200000073 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-875 | EQ-2000-68856 | 3 | Medium | MP-2000-028 | LUBR | Lubrication | DLT | Deleted | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-04 | 2025-02-07 00:00 | 2025-02-08 05:00 |  |  | 3591.56 |  | 52 |  | NONE
40200000074 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-364 | EQ-2000-51910 | 3 | Medium | MP-2000-034 | TEST | Testing | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-08 | 2025-02-21 00:00 | 2025-02-21 10:00 | 2025-02-21 10:03 | 2025-02-21 23:03 | 14130.92 | 14130.92 | 67.1 | 78.1 | NONE
40200000075 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-701 | EQ-2000-78493 | 2 | High | MP-2000-007 | TEST | Testing | REL | Released | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-09 | 2025-02-16 00:00 | 2025-02-16 16:00 |  |  | 4166.24 |  | 68.9 |  | NONE
40200000076 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-988 | EQ-2000-80206 | 2 | High | MP-2000-026 | CLEA | Cleaning | CNF | Confirmed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-05 | 2025-02-12 00:00 | 2025-02-13 11:00 | 2025-02-12 09:46 | 2025-02-14 12:46 | 14514.57 | 14514.57 | 57.8 | 57.8 | NONE
40200000077 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-505 | EQ-2000-53449 | 3 | Medium | MP-2000-020 | CLEA | Cleaning | REL | Released | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-08 | 2025-02-12 00:00 | 2025-02-12 08:00 |  |  |  |  | 107.8 |  | NONE