## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000094 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-544 | EQ-2000-93032 | 2 | High |  | TEST | Testing | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-20 | 2025-02-27 00:00 | 2025-03-01 08:00 | 2025-02-27 00:00 | 2025-03-01 15:00 | 614.39 | 614.39 | 65 | 65 | ELEC | AGE |  | NT-2000-118786
40200000095 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-741 | EQ-2000-42613 | 3 | Medium | MP-2000-011 | CALI | Calibration | PCNF | Partially Confirmed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-18 | 2025-03-02 00:00 | 2025-03-03 22:00 | 2025-03-02 06:47 |  | 3658.8 |  | 47.3 |  | NONE
40200000096 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-397 | EQ-2000-69759 | 4 | Low | MP-2000-032 | TEST | Testing | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-22 | 2025-03-03 00:00 | 2025-03-05 21:00 | 2025-03-03 00:53 | 2025-03-04 21:53 | 22255.36 | 22255.36 | 119.5 | 119.5 | NONE
40200000097 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-931 | EQ-2000-62873 | 2 | High | MP-2000-024 | LUBR | Lubrication | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-17 | 2025-02-21 00:00 | 2025-02-22 06:00 | 2025-02-21 00:00 | 2025-02-21 18:00 | 18484.88 | 18484.88 | 71.6 | 88.2 | NONE
40200000098 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-CONV-997 | EQ-2000-93928 | 3 | Medium | MP-2000-045 | INSP | Inspection | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-19 | 2025-03-04 00:00 | 2025-03-06 22:00 | 2025-03-04 00:00 | 2025-03-04 08:00 |  | 16718.26 | 79.1 | 79.1 | NONE
40200000099 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-489 | EQ-2000-26199 | 3 | Medium | MP-2000-043 | LUBR | Lubrication | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-21 | 2025-02-26 00:00 | 2025-02-28 14:00 | 2025-02-26 00:00 | 2025-02-26 21:00 | 17532.2 | 17532.2 | 76.4 | 77.6 | NONE
40200000100 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-720 | EQ-2000-27978 | 1 | Very High |  | REPR | Repair | CNF | Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-20 | 2025-03-06 00:00 | 2025-03-06 15:00 | 2025-03-06 00:00 | 2025-03-08 19:00 | 7426.32 | 7862.77 | 94.6 | 94.6 | NOIS | OPER |  | NT-2000-475308
40200000101 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-402 | EQ-2000-31020 | 2 | High | MP-2000-001 | LUBR | Lubrication | DLT | Deleted | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-17 | 2025-02-26 00:00 | 2025-02-28 17:00 |  |  | 17361 |  | 58.7 |  | NONE
40200000102 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-955 | EQ-2000-85255 | 4 | Low | MP-2000-015 | REPR | Repair | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-22 | 2025-03-02 00:00 | 2025-03-02 21:00 | 2025-03-02 01:06 | 2025-03-02 14:06 | 18227.31 | 18554.25 | 14 | 14 | NONE
40200000103 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-TURB-575 | EQ-2000-16564 | 4 | Low |  | INSP | Inspection | REL | Released | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-17 | 2025-03-03 00:00 | 2025-03-04 00:00 |  |  | 21380.09 |  | 44.5 |  | ELEC | DSGN |  | NT-2000-110142
40200000104 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-779 | EQ-2000-94829 | 2 | High |  | CALI | Calibration | CNF | Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-18 | 2025-02-24 00:00 | 2025-02-25 23:00 | 2025-02-24 00:00 | 2025-02-26 10:00 | 22022.65 | 27677.1 | 13 | 13 | ELEC | OPER |  | NT-2000-385037
40200000105 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-806 | EQ-2000-72684 | 3 | Medium |  | OVHL | Overhaul | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-23 | 2025-03-02 00:00 | 2025-03-02 23:00 | 2025-03-02 00:00 | 2025-03-02 16:00 | 17556.16 | 20564.39 | 8.9 | 8.9 | OVER | AGE |  | NT-2000-941235
40200000106 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-794 | EQ-2000-67430 | 2 | High |  | INSP | Inspection | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-18 | 2025-02-28 00:00 | 2025-03-02 02:00 | 2025-02-28 12:56 | 2025-03-02 11:56 | 21633.11 | 21633.11 | 105.8 | 126.8 | OVER | DSGN |  | NT-2000-562094
40200000107 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-164 | EQ-2000-44290 | 3 | Medium | MP-2000-034 | LUBR | Lubrication | REL | Released | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-22 | 2025-02-28 00:00 | 2025-02-28 03:00 |  |  | 24458.44 |  | 81 |  | NONE
40200000108 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-777 | EQ-2000-42581 | 2 | High |  | INSP | Inspection | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-20 | 2025-02-26 00:00 | 2025-02-28 03:00 | 2025-02-26 01:47 | 2025-02-26 22:47 | 785.3 | 1022.47 | 112.3 | 121 | NONE | DSGN |  | NT-2000-887931