## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000109 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-428 | EQ-2000-41574 | 2 | High | MP-2000-006 | LUBR | Lubrication | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-26 | 2025-03-03 00:00 | 2025-03-03 08:00 | 2025-03-03 00:00 | 2025-03-05 18:00 | 13987.14 | 16712.14 | 46.7 | 46.7 | NONE
40200000110 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-558 | EQ-2000-21536 | 3 | Medium | MP-2000-007 | REPL | Replacement | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-02 | 2025-03-10 00:00 | 2025-03-12 11:00 | 2025-03-10 00:00 |  | 3408.32 |  | 60.7 |  | NONE
40200000111 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-670 | EQ-2000-81971 | 2 | High | MP-2000-030 | CALI | Calibration | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-24 | 2025-03-10 00:00 | 2025-03-10 13:00 | 2025-03-10 00:00 | 2025-03-13 07:00 | 22307.72 | 25250.98 | 68.4 | 80.1 | NONE
40200000112 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-936 | EQ-2000-39218 | 2 | High | MP-2000-007 | CLEA | Cleaning | REL | Released | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-02 | 2025-03-10 00:00 | 2025-03-11 20:00 |  |  | 18058.12 |  | 44.9 |  | NONE
40200000113 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-449 | EQ-2000-56548 | 4 | Low | MP-2000-009 | REPL | Replacement | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-02 | 2025-03-13 00:00 | 2025-03-14 15:00 | 2025-03-13 07:52 | 2025-03-16 07:52 | 17701.35 | 17701.35 | 7.4 | 7.8 | NONE
40200000114 | PM05 | Emergency Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-360 | EQ-2000-90065 | 3 | Medium |  | LUBR | Lubrication | CNF | Confirmed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-25 | 2025-03-01 00:00 | 2025-03-01 17:00 | 2025-03-01 00:20 | 2025-03-03 04:20 | 11697.63 | 12168.91 | 94.2 | 127.7 | ELEC | AGE | X | NT-2000-909652
40200000115 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-568 | EQ-2000-96305 | 3 | Medium | MP-2000-028 | CLEA | Cleaning | REL | Released | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-28 | 2025-03-09 00:00 | 2025-03-09 19:00 |  |  | 606.27 |  | 88.9 |  | NONE
40200000116 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-899 | EQ-2000-33226 | 4 | Low | MP-2000-033 | REPR | Repair | CNF | Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-01 | 2025-03-11 00:00 | 2025-03-12 00:00 | 2025-03-11 03:02 | 2025-03-11 21:02 | 9991.44 | 9991.44 | 72.9 | 72.9 | NONE
40200000117 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-809 | EQ-2000-42537 | 3 | Medium |  | CLEA | Cleaning | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-26 | 2025-03-05 00:00 | 2025-03-06 21:00 | 2025-03-05 00:00 | 2025-03-06 15:00 | 20217.52 | 20217.52 | 18.3 | 20 | NONE | MATL |  | NT-2000-846454
40200000118 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-747 | EQ-2000-38487 | 3 | Medium | MP-2000-033 | OVHL | Overhaul | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-25 | 2025-03-01 00:00 | 2025-03-02 15:00 | 2025-03-01 00:00 | 2025-03-02 22:00 | 24542.72 | 24542.72 | 78.7 | 87.1 | NONE
40200000119 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-879 | EQ-2000-56168 | 3 | Medium | MP-2000-007 | CALI | Calibration | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-02-28 | 2025-03-08 00:00 | 2025-03-10 07:00 | 2025-03-08 05:19 | 2025-03-11 03:19 |  | 24421.67 | 51.8 | 51.8 | NONE
40200000120 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-154 | EQ-2000-97851 | 4 | Low |  | CALI | Calibration | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-24 | 2025-02-28 00:00 | 2025-03-01 12:00 | 2025-02-28 03:01 | 2025-03-01 01:01 | 17243.06 | 18276.84 | 19.3 | 19.3 | LEAK | UNKN |  | NT-2000-476105
40200000121 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-204 | EQ-2000-90754 | 2 | High | MP-2000-019 | TEST | Testing | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-02 | 2025-03-13 00:00 | 2025-03-14 06:00 | 2025-03-13 02:57 | 2025-03-16 03:57 | 6321.09 | 7007.19 | 94.5 | 142.7 | NONE
40200000122 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-496 | EQ-2000-64600 | 2 | High |  | INSP | Inspection | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-02 | 2025-03-13 00:00 | 2025-03-14 18:00 | 2025-03-13 06:27 | 2025-03-16 06:27 | 817.65 | 910.05 | 31.7 | 35.7 | NOIS | OPER |  | NT-2000-891787
40200000123 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-659 | EQ-2000-89087 | 5 | Unknown | MP-2000-012 | CALI | Calibration | PCNF | Partially Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-25 | 2025-03-10 00:00 | 2025-03-11 02:00 | 2025-03-10 00:00 |  | 11495.97 |  | 118 |  | NONE
40200000124 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-141 | EQ-2000-66165 | 3 | Medium | MP-2000-030 | OVHL | Overhaul | DLT | Deleted | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-02-26 | 2025-03-07 00:00 | 2025-03-08 11:00 |  |  |  |  | 101.8 |  | NONE