## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000032 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-666 | EQ-2000-88774 | 4 | Low | MP-2000-026 | CALI | Calibration | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-24 | 2025-02-05 00:00 | 2025-02-06 14:00 | 2025-02-05 09:26 | 2025-02-05 14:26 | 5533.42 | 6931.1 | 73.6 | 73.6 | NONE
40200000033 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-606 | EQ-2000-60578 | 4 | Low |  | REPR | Repair | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-20 | 2025-01-24 00:00 | 2025-01-26 17:00 | 2025-01-24 00:00 | 2025-01-27 06:00 | 13443.02 | 13443.02 | 117.4 | 142.1 | ELEC | MATL |  | NT-2000-483162
40200000034 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-799 | EQ-2000-32645 | 3 | Medium | MP-2000-026 | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-26 | 2025-02-03 00:00 | 2025-02-03 11:00 | 2025-02-03 01:04 | 2025-02-03 05:04 | 837.94 | 837.94 | 27.5 | 31.1 | NONE
40200000035 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-885 | EQ-2000-64451 | 4 | Low | MP-2000-006 | REPR | Repair | PCNF | Partially Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-23 | 2025-02-04 00:00 | 2025-02-06 05:00 | 2025-02-04 04:35 |  | 16193.16 |  | 65.4 |  | NONE
40200000036 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-308 | EQ-2000-30365 | 2 | High |  | REPR | Repair | CLSD | Closed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-24 | 2025-01-30 00:00 | 2025-02-01 04:00 | 2025-01-30 00:00 | 2025-02-02 05:00 | 8099.15 | 9036.67 | 53.6 | 53.6 | WEAR | AGE |  | NT-2000-575394
40200000037 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-723 | EQ-2000-17212 | 3 | Medium | MP-2000-032 | REPR | Repair | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-22 | 2025-02-02 00:00 | 2025-02-03 00:00 | 2025-02-02 04:59 |  |  |  | 18.2 |  | NONE
40200000038 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-480 | EQ-2000-26637 | 3 | Medium | MP-2000-017 | INSP | Inspection | CNF | Confirmed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-25 | 2025-02-07 00:00 | 2025-02-08 12:00 | 2025-02-07 00:00 | 2025-02-07 17:00 | 8707.77 | 8707.77 | 52.7 | 59 | NONE
40200000039 | PM05 | Emergency Maintenance | 2000 | Plant B - Chicago | CHI-CONV-566 | EQ-2000-76949 | 3 | Medium |  | OVHL | Overhaul | CNF | Confirmed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-22 | 2025-01-23 00:00 | 2025-01-25 17:00 | 2025-01-23 00:00 | 2025-01-26 02:00 | 9508.35 | 9870.87 | 32.1 | 32.1 | VIBR | ENVR | X | NT-2000-876764
40200000040 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-102 | EQ-2000-15772 | 3 | Medium | MP-2000-003 | INSP | Inspection | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-26 | 2025-02-09 00:00 | 2025-02-09 03:00 | 2025-02-09 07:24 | 2025-02-10 16:24 | 12058.23 | 12058.23 | 47.2 | 47.2 | NONE
40200000041 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-429 | EQ-2000-42540 | 3 | Medium | MP-2000-004 | REPR | Repair | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-23 | 2025-02-04 00:00 | 2025-02-05 18:00 | 2025-02-04 07:17 | 2025-02-05 19:17 | 14502.63 | 14502.63 | 16.1 | 18.1 | NONE
40200000042 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-147 | EQ-2000-62550 | 2 | High | MP-2000-013 | CALI | Calibration | REL | Released | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-20 | 2025-01-28 00:00 | 2025-01-29 14:00 |  |  |  |  | 67.3 |  | NONE
40200000043 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-348 | EQ-2000-70807 | 2 | High | MP-2000-035 | LUBR | Lubrication | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-22 | 2025-02-01 00:00 | 2025-02-03 17:00 | 2025-02-01 07:47 | 2025-02-02 10:47 |  | 4188.88 | 112 | 112 | NONE
40200000044 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-101 | EQ-2000-96154 | 2 | High | MP-2000-004 | LUBR | Lubrication | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-23 | 2025-02-06 00:00 | 2025-02-07 17:00 | 2025-02-06 05:29 | 2025-02-06 20:29 | 13480.45 | 14181.07 | 30.1 | 37.6 | NONE
40200000045 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-144 | EQ-2000-40339 | 3 | Medium |  | REPL | Replacement | PCNF | Partially Confirmed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-01-26 | 2025-02-04 00:00 | 2025-02-06 06:00 | 2025-02-04 00:00 |  | 11732.22 |  | 90.3 |  | VIBR | ENVR |  | NT-2000-720647
40200000046 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-163 | EQ-2000-67014 | 3 | Medium | MP-2000-048 | CALI | Calibration | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-01-25 | 2025-01-28 00:00 | 2025-01-29 08:00 | 2025-01-28 03:40 | 2025-01-29 18:40 | 21347.39 | 21347.39 | 111.3 | 111.3 | NONE