## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000125 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-257 | EQ-2000-52287 | 3 | Medium | MP-2000-012 | REPL | Replacement | CLSD | Closed | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-07 | 2025-03-08 00:00 | 2025-03-09 16:00 | 2025-03-08 00:00 | 2025-03-10 16:00 | 2285.58 | 2374.94 | 85.5 | 85.5 | NONE
40200000126 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-263 | EQ-2000-64516 | 3 | Medium | MP-2000-022 | REPR | Repair | PCNF | Partially Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-07 | 2025-03-16 00:00 | 2025-03-18 05:00 | 2025-03-16 11:34 |  | 9060.37 |  | 106.2 |  | NONE
40200000127 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-870 | EQ-2000-91039 | 1 | Very High | MP-2000-040 | REPL | Replacement | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-07 | 2025-03-15 00:00 | 2025-03-15 03:00 | 2025-03-15 00:00 | 2025-03-15 16:00 | 11418.85 | 11418.85 | 108.7 | 108.7 | NONE
40200000128 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-490 | EQ-2000-24860 | 3 | Medium | MP-2000-033 | INSP | Inspection | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-06 | 2025-03-11 00:00 | 2025-03-13 23:00 | 2025-03-11 10:21 | 2025-03-13 00:21 | 22827.73 | 22827.73 | 99 | 108.4 | NONE
40200000129 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-403 | EQ-2000-95397 | 3 | Medium | MP-2000-001 | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-04 | 2025-03-10 00:00 | 2025-03-12 19:00 | 2025-03-10 05:35 | 2025-03-10 17:35 | 4601.17 | 5406.29 | 114.8 | 114.8 | NONE
40200000130 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-786 | EQ-2000-92511 | 3 | Medium | MP-2000-050 | LUBR | Lubrication | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-09 | 2025-03-13 00:00 | 2025-03-15 08:00 | 2025-03-13 00:00 | 2025-03-13 15:00 | 13674.98 | 14053.54 | 84.9 | 115.3 | NONE
40200000131 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-124 | EQ-2000-70191 | 3 | Medium | MP-2000-037 | REPR | Repair | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-08 | 2025-03-14 00:00 | 2025-03-14 06:00 | 2025-03-14 12:02 | 2025-03-15 01:02 | 1829.57 | 1829.57 | 95.7 | 116.3 | NONE
40200000132 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-497 | EQ-2000-69129 | 3 | Medium | MP-2000-042 | REPL | Replacement | REL | Released | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-08 | 2025-03-15 00:00 | 2025-03-17 09:00 |  |  | 913.83 |  | 81.4 |  | NONE
40200000133 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-146 | EQ-2000-19514 | 3 | Medium | MP-2000-025 | CALI | Calibration | CLSD | Closed | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-05 | 2025-03-14 00:00 | 2025-03-14 15:00 | 2025-03-14 05:41 | 2025-03-15 20:41 | 15360.86 | 16932.36 | 35.2 | 35.2 | NONE
40200000134 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-260 | EQ-2000-79922 | 3 | Medium | MP-2000-047 | CALI | Calibration | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-04 | 2025-03-07 00:00 | 2025-03-09 04:00 | 2025-03-07 04:48 | 2025-03-10 03:48 | 24023.29 | 24023.29 | 19 | 19.5 | NONE
40200000135 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-666 | EQ-2000-82754 | 3 | Medium | MP-2000-006 | INSP | Inspection | DLT | Deleted | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-04 | 2025-03-06 00:00 | 2025-03-06 07:00 |  |  | 14531.61 |  | 48.5 |  | NONE
40200000136 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-TURB-316 | EQ-2000-64087 | 3 | Medium | MP-2000-008 | OVHL | Overhaul | TECO | Technically Complete | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-08 | 2025-03-22 00:00 | 2025-03-24 19:00 | 2025-03-22 07:19 | 2025-03-23 03:19 | 5007.82 | 5445.08 | 74.8 | 75.2 | NONE
40200000137 | PM04 | Predictive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-572 | EQ-2000-94498 | 2 | High | MP-2000-022 | CALI | Calibration | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-07 | 2025-03-09 00:00 | 2025-03-10 15:00 | 2025-03-09 00:00 | 2025-03-09 10:00 | 2905.96 | 2905.96 | 87.6 | 98.1 | NONE
40200000138 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-202 | EQ-2000-47373 | 3 | Medium | MP-2000-045 | REPL | Replacement | CRTD | Created | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-07 | 2025-03-09 00:00 | 2025-03-10 02:00 |  |  | 12403.6 |  | 40.7 |  | NONE
40200000139 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-680 | EQ-2000-57774 | 4 | Low | MP-2000-042 | INSP | Inspection | CNF | Confirmed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-09 | 2025-03-15 00:00 | 2025-03-17 08:00 | 2025-03-15 00:00 | 2025-03-15 23:00 | 8173.76 | 8382.56 | 94.7 | 119 | NONE