## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40200000156 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-CONV-470 | EQ-2000-23970 | 4 | Low |  | TEST | Testing | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-18 | 2025-03-25 00:00 | 2025-03-26 10:00 | 2025-03-25 03:04 | 2025-03-26 14:04 | 14334.42 | 16233.25 | 74.2 | 76.8 | BLOC | OPER |  | NT-2000-287401
40200000157 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-TURB-672 | EQ-2000-82733 | 3 | Medium |  | REPL | Replacement | REL | Released | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-20 | 2025-03-25 00:00 | 2025-03-26 17:00 |  |  | 19467.76 |  | 49 |  | OVER | UNKN |  | NT-2000-921149
40200000158 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-COMP-202 | EQ-2000-38109 | 4 | Low | MP-2000-006 | INSP | Inspection | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-21 | 2025-03-28 00:00 | 2025-03-29 21:00 | 2025-03-28 00:40 | 2025-03-31 00:40 |  | 4438.08 | 115.8 | 142.9 | NONE
40200000159 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-545 | EQ-2000-21552 | 3 | Medium | MP-2000-026 | REPR | Repair | CLSD | Closed | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-17 | 2025-03-22 00:00 | 2025-03-23 06:00 | 2025-03-22 00:00 | 2025-03-24 01:00 | 15421.21 | 17191.7 | 87.5 | 88.5 | NONE
40200000160 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-158 | EQ-2000-32973 | 2 | High |  | LUBR | Lubrication | TECO | Technically Complete | INST-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-22 | 2025-03-30 00:00 | 2025-04-01 10:00 | 2025-03-30 00:00 | 2025-03-30 03:00 | 21338.91 | 24635.65 | 111.8 | 111.8 | NONE | MATL |  | NT-2000-745073
40200000161 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-790 | EQ-2000-14726 | 4 | Low | MP-2000-026 | REPR | Repair | TECO | Technically Complete | ELEC-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-19 | 2025-03-23 00:00 | 2025-03-23 02:00 | 2025-03-23 00:00 | 2025-03-23 22:00 | 24922.02 | 24922.02 | 94 | 94 | NONE
40200000162 | PM03 | Condition-Based Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-115 | EQ-2000-18993 | 2 | High | MP-2000-013 | REPL | Replacement | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-17 | 2025-03-26 00:00 | 2025-03-27 14:00 | 2025-03-26 00:08 | 2025-03-29 01:08 | 9013.14 | 10922.42 | 98.2 | 101.5 | NONE
40200000163 | PM05 | Emergency Maintenance | 2000 | Plant B - Chicago | CHI-HEAT-104 | EQ-2000-44223 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | INST-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-18 | 2025-03-25 00:00 | 2025-03-27 18:00 | 2025-03-25 02:42 | 2025-03-25 17:42 | 12827.64 | 12827.64 | 42.1 | 42.1 | VIBR | ENVR | X | NT-2000-827912
40200000164 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-486 | EQ-2000-83815 | 3 | Medium | MP-2000-031 | CLEA | Cleaning | TECO | Technically Complete | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-20 | 2025-04-02 00:00 | 2025-04-03 09:00 | 2025-04-02 03:28 | 2025-04-04 00:28 | 17199.07 | 18039.58 | 107.8 | 117.4 | NONE
40200000165 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-491 | EQ-2000-93055 | 4 | Low | MP-2000-017 | TEST | Testing | CLSD | Closed | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-23 | 2025-03-27 00:00 | 2025-03-28 07:00 | 2025-03-27 00:00 | 2025-03-28 18:00 |  | 30391.94 | 62.9 | 70.5 | NONE
40200000166 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-508 | EQ-2000-98302 | 3 | Medium | MP-2000-018 | OVHL | Overhaul | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-22 | 2025-04-05 00:00 | 2025-04-06 21:00 | 2025-04-05 00:00 | 2025-04-05 11:00 | 12175.61 | 12175.61 | 43.7 | 57.2 | NONE
40200000167 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-CONV-854 | EQ-2000-36170 | 2 | High | MP-2000-023 | LUBR | Lubrication | CLSD | Closed | MECH-C1 | PLN-C01 | CC-CHI-MNT | 2025-03-18 | 2025-03-30 00:00 | 2025-03-31 08:00 | 2025-03-30 00:00 | 2025-03-31 11:00 | 6115.58 | 6115.58 | 100.5 | 100.5 | NONE
40200000168 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-PUMP-180 | EQ-2000-98580 | 3 | Medium | MP-2000-037 | INSP | Inspection | CLSD | Closed | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-22 | 2025-03-30 00:00 | 2025-03-30 02:00 | 2025-03-30 07:18 | 2025-04-02 06:18 | 21276.26 | 26131.45 | 45.8 | 57.2 | NONE
40200000169 | PM02 | Corrective Maintenance | 2000 | Plant B - Chicago | CHI-COMP-882 |  | 4 | Low |  | OVHL | Overhaul | TECO | Technically Complete | ELEC-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-19 | 2025-03-26 00:00 | 2025-03-27 06:00 | 2025-03-26 00:00 | 2025-03-29 03:00 | 1826.63 | 1928.68 | 96.3 | 96.3 | NOIS | ENVR |  | NT-2000-819678
40200000170 | PM01 | Preventive Maintenance | 2000 | Plant B - Chicago | CHI-COMP-568 | EQ-2000-25776 | 3 | Medium | MP-2000-038 | REPL | Replacement | REL | Released | MECH-C1 | PLN-C02 | CC-CHI-MNT | 2025-03-22 | 2025-03-31 00:00 | 2025-04-02 12:00 |  |  | 17385.66 |  | 3.4 |  | NONE