## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000063 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-941 | EQ-3000-68355 | 2 | High |  | REPR | Repair | TECO | Technically Complete | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-04 | 2025-02-09 00:00 | 2025-02-11 05:00 | 2025-02-09 00:00 | 2025-02-09 10:00 | 17294.96 | 19333.22 | 72.4 | 72.4 | BLOC | MATL | X | NT-3000-194930
40300000064 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-936 | EQ-3000-28208 | 2 | High | MP-3000-029 | OVHL | Overhaul | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-07 | 2025-02-20 00:00 | 2025-02-20 02:00 | 2025-02-20 00:00 | 2025-02-20 20:00 | 11597.87 | 11597.87 | 36.4 | 36.8 | NONE
40300000065 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-406 | EQ-3000-84747 | 3 | Medium |  | TEST | Testing | CRTD | Created | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-09 | 2025-02-20 00:00 | 2025-02-21 16:00 |  |  |  |  | 110 |  | VIBR | ENVR |  | NT-3000-988811
40300000066 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-972 | EQ-3000-48559 | 4 | Low |  | INSP | Inspection | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-03 | 2025-02-09 00:00 | 2025-02-12 00:00 | 2025-02-09 00:00 | 2025-02-09 08:00 | 17732.18 | 22469.3 | 98.8 | 117.9 | ELEC | AGE |  | NT-3000-552686
40300000067 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-503 | EQ-3000-91948 | 4 | Low |  | TEST | Testing | REL | Released | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-05 | 2025-02-17 00:00 | 2025-02-19 02:00 |  |  | 9848.34 |  | 66.3 |  | OVER | DSGN |  | NT-3000-984293
40300000068 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-960 | EQ-3000-64687 | 4 | Low | MP-3000-032 | INSP | Inspection | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-04 | 2025-02-09 00:00 | 2025-02-09 18:00 | 2025-02-09 12:37 | 2025-02-10 07:37 | 2257.78 | 2363.66 | 3.9 | 3.9 | NONE
40300000069 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-186 | EQ-3000-27985 | 3 | Medium | MP-3000-029 | TEST | Testing | CLSD | Closed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-02-08 | 2025-02-21 00:00 | 2025-02-23 07:00 | 2025-02-21 00:00 | 2025-02-23 12:00 | 15769.59 | 17951.09 | 55.6 | 69.4 | NONE
40300000070 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-COMP-290 | EQ-3000-65675 | 4 | Low |  | LUBR | Lubrication | CRTD | Created | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-07 | 2025-02-08 00:00 | 2025-02-10 17:00 |  |  | 17947.18 |  | 33.8 |  | NONE | ENVR | X | NT-3000-839122
40300000071 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-TURB-215 | EQ-3000-86056 | 3 | Medium |  | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-06 | 2025-02-18 00:00 | 2025-02-18 12:00 | 2025-02-18 00:00 | 2025-02-18 20:00 | 11890.94 | 11890.94 | 11.2 | 11.2 | VIBR | OPER | X | NT-3000-817303
40300000072 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-917 | EQ-3000-85973 | 1 | Very High |  | INSP | Inspection | CNF | Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-02-05 | 2025-02-15 00:00 | 2025-02-15 08:00 | 2025-02-15 02:45 | 2025-02-16 23:45 | 11987.29 | 11987.29 | 62.5 | 63.4 | NOIS | ENVR |  | NT-3000-936997
40300000073 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-TURB-396 | EQ-3000-31955 | 4 | Low | MP-3000-004 | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-03 | 2025-02-15 00:00 | 2025-02-16 16:00 | 2025-02-15 23:56 | 2025-02-19 01:56 | 2004.74 | 2366.72 | 57.8 | 61.3 | NONE
40300000074 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-127 | EQ-3000-47593 | 3 | Medium | MP-3000-018 | REPR | Repair | CNF | Confirmed | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-02-06 | 2025-02-08 00:00 | 2025-02-08 18:00 | 2025-02-08 00:00 | 2025-02-10 18:00 | 21360.41 | 22478.47 | 34.8 | 45.5 | NONE
40300000075 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-859 | EQ-3000-24621 | 2 | High | MP-3000-032 | REPL | Replacement | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-07 | 2025-02-10 00:00 | 2025-02-10 21:00 | 2025-02-10 10:41 | 2025-02-12 21:41 | 20292.1 | 20292.1 | 32.8 | 44.8 | NONE
40300000076 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-TURB-186 | EQ-3000-29014 | 3 | Medium | MP-3000-041 | TEST | Testing | CNF | Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-07 | 2025-02-21 00:00 | 2025-02-21 21:00 | 2025-02-21 01:11 | 2025-02-23 18:11 | 19374.01 | 22666.7 | 30.1 | 37.5 | NONE
40300000077 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-HEAT-851 | EQ-3000-55229 | 1 | Very High | MP-3000-031 | REPR | Repair | PCNF | Partially Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-03 | 2025-02-14 00:00 | 2025-02-15 11:00 | 2025-02-14 01:23 |  | 1786.82 |  | 56.8 |  | NONE