## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000078 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-799 | EQ-3000-61127 | 3 | Medium | MP-3000-044 | TEST | Testing | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-13 | 2025-02-18 00:00 | 2025-02-18 20:00 | 2025-02-18 00:00 | 2025-02-20 21:00 | 790.64 | 891.61 | 111.4 | 162.1 | NONE
40300000077 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-644 | EQ-3000-93548 | 3 | Medium | MP-3000-042 | CALI | Calibration | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-12 | 2025-02-26 00:00 | 2025-02-28 09:00 | 2025-02-26 04:04 | 2025-03-01 12:04 | 8706.7 | 12434.45 | 33.5 | 33.5 | NONE
40300000080 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-891 | EQ-3000-98511 | 1 | Very High |  | REPL | Replacement | PCNF | Partially Confirmed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-15 | 2025-02-19 00:00 | 2025-02-20 02:00 | 2025-02-19 00:00 |  |  |  | 119.2 |  | ELEC | ENVR |  | NT-3000-112542
40300000081 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-200 | EQ-3000-78847 | 4 | Low | MP-3000-002 | REPL | Replacement | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-10 | 2025-02-21 00:00 | 2025-02-23 11:00 |  |  | 5875.7 |  | 35.4 |  | NONE
40300000082 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-708 | EQ-3000-96062 | 4 | Low | MP-3000-042 | REPR | Repair | CNF | Confirmed | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-16 | 2025-02-20 00:00 | 2025-02-20 17:00 | 2025-02-20 00:48 | 2025-02-20 17:48 | 21482.8 | 21482.8 | 17.3 | 19.8 | NONE
40300000083 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-812 | EQ-3000-34151 | 3 | Medium |  | REPR | Repair | REL | Released | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-12 | 2025-02-17 00:00 | 2025-02-19 13:00 |  |  | 16150.12 |  | 110.9 |  | CORR | DSGN |  | NT-3000-369836
40300000084 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-COMP-899 | EQ-3000-19698 | 4 | Low | MP-3000-017 | TEST | Testing | PCNF | Partially Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-12 | 2025-02-25 00:00 | 2025-02-25 09:00 | 2025-02-25 05:24 |  | 10020.47 |  | 119.5 |  | NONE
40300000085 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-603 | EQ-3000-36302 | 2 | High | MP-3000-042 | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-14 | 2025-02-21 00:00 | 2025-02-22 00:00 | 2025-02-21 04:13 | 2025-02-23 20:13 | 4024.88 | 4024.88 | 92.7 | 112.7 | NONE
40300000086 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-TURB-205 | EQ-3000-14569 | 3 | Medium | MP-3000-001 | CLEA | Cleaning | PCNF | Partially Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-10 | 2025-02-12 00:00 | 2025-02-13 10:00 | 2025-02-12 13:52 |  | 959.74 |  | 60.7 |  | NONE
40300000087 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-255 | EQ-3000-53231 | 1 | Very High |  | CLEA | Cleaning | CRTD | Created | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-02-13 | 2025-02-23 00:00 | 2025-02-23 02:00 |  |  | 12214.42 |  | 49.7 |  | VIBR | ENVR |  | NT-3000-227091
40300000088 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-HEAT-648 | EQ-3000-57044 | 4 | Low |  | INSP | Inspection | CNF | Confirmed | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-12 | 2025-02-23 00:00 | 2025-02-24 16:00 | 2025-02-23 08:16 | 2025-02-25 13:16 | 15990.68 | 15990.68 | 115.1 | 134.8 | VIBR | MATL |  | NT-3000-982042
40300000089 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-878 | EQ-3000-48005 | 4 | Low |  | INSP | Inspection | CLSD | Closed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-15 | 2025-02-19 00:00 | 2025-02-20 00:00 | 2025-02-19 02:09 | 2025-02-22 02:09 | 24204.07 | 24204.07 | 80 | 83.7 | CORR | UNKN |  | NT-3000-610135
40300000090 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-747 | EQ-3000-67407 | 2 | High | MP-3000-025 | LUBR | Lubrication | CNF | Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-15 | 2025-02-19 00:00 | 2025-02-19 19:00 | 2025-02-19 00:00 | 2025-02-19 06:00 | 1121.43 | 1358.76 | 119.6 | 121.2 | NONE
40300000091 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-CONV-646 | EQ-3000-68891 | 1 | Very High |  | REPL | Replacement | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-10 | 2025-02-11 00:00 | 2025-02-12 21:00 | 2025-02-11 00:00 | 2025-02-11 09:00 | 19800.57 | 19800.57 | 7.1 | 7.8 | VIBR | OPER | X | NT-3000-811016
40300000092 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-HEAT-252 | EQ-3000-85936 | 3 | Medium |  | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-11 | 2025-02-13 00:00 | 2025-02-13 06:00 | 2025-02-13 05:48 | 2025-02-14 01:48 | 16518.87 | 16518.87 | 57.6 | 69.6 | LEAK | OPER | X | NT-3000-280616
40300000093 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-414 | EQ-3000-22752 | 3 | Medium | MP-3000-040 | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-13 | 2025-02-23 00:00 | 2025-02-23 23:00 | 2025-02-23 00:00 | 2025-02-26 05:00 | 20536.1 | 20748.52 | 14.5 | 14.5 | NONE