## PM_Orders
Order_Number | Order_Type | Order_Type_Desc | Plant | Plant_Name | Functional_Location | Equipment_ID | Priority | Priority_Desc | Maintenance_Plan | Activity_Type | Activity_Type_Desc | Status | Status_Desc | Work_Center | Planner_Group | Cost_Center | Created_Date | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Planned_Cost_USD | Actual_Cost_USD | Planned_Labor_Hours | Actual_Labor_Hours | Damage_Code | Cause_Code | Breakdown_Indicator | Notification_Number
40300000109 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-890 | EQ-3000-28169 | 5 | Unknown |  | REPL | Replacement | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-02 | 2025-03-14 00:00 | 2025-03-16 05:00 | 2025-03-14 21:31 | 2025-03-15 22:31 | 15856.87 | 15856.87 | 85.1 | 85.1 | LEAK | UNKN |  | NT-3000-656710
40300000110 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-PUMP-403 | EQ-3000-65823 | 3 | Medium |  | LUBR | Lubrication | PCNF | Partially Confirmed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-03-02 | 2025-03-07 00:00 | 2025-03-09 23:00 | 2025-03-07 03:49 |  | 19798.45 |  | 11.6 |  | ELEC | UNKN |  | NT-3000-154067
40300000111 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-PUMP-492 | EQ-3000-57918 | 3 | Medium | MP-3000-036 | REPL | Replacement | DLT | Deleted | INST-D1 | PLN-D01 | CC-DET-MNT | 2025-02-27 | 2025-03-09 00:00 | 2025-03-09 07:00 |  |  | 9477.61 |  | 78.5 |  | NONE
40300000112 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-COMP-442 | EQ-3000-41278 | 3 | Medium | MP-3000-018 | LUBR | Lubrication | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-28 | 2025-03-02 00:00 | 2025-03-04 15:00 | 2025-03-02 16:37 | 2025-03-05 20:37 | 18952.75 | 18952.75 | 91.8 | 91.8 | NONE
40300000113 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-155 | EQ-3000-18305 | 3 | Medium |  | REPR | Repair | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-26 | 2025-03-04 00:00 | 2025-03-06 11:00 | 2025-03-04 07:00 | 2025-03-06 23:00 | 12019.01 | 15171.49 | 64.8 | 80.9 | NONE | MATL |  | NT-3000-297503
40300000114 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-CONV-189 | EQ-3000-20508 | 4 | Low |  | REPR | Repair | TECO | Technically Complete | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-27 | 2025-03-02 00:00 | 2025-03-03 14:00 | 2025-03-02 11:59 | 2025-03-02 22:59 | 4536.77 | 5277.34 | 15.2 | 18.5 | OVER | DSGN |  | NT-3000-407410
40300000115 | PM01 | Preventive Maintenance | 3000 | Plant C - Detroit | DET-CONV-798 | EQ-3000-80966 | 3 | Medium | MP-3000-002 | CLEA | Cleaning | CNF | Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-25 | 2025-03-05 00:00 | 2025-03-06 22:00 | 2025-03-05 00:00 | 2025-03-07 07:00 | 18573.88 | 23379.52 | 4.5 | 5.6 | NONE
40300000116 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-692 | EQ-3000-54930 | 4 | Low | MP-3000-020 | CLEA | Cleaning | TECO | Technically Complete | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-03-01 | 2025-03-12 00:00 | 2025-03-13 19:00 | 2025-03-12 00:00 | 2025-03-14 16:00 | 11721.17 | 12212.7 | 68.9 | 81.9 | NONE
40300000117 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-595 | EQ-3000-58745 | 1 | Very High |  | REPL | Replacement | CLSD | Closed | MECH-D1 | PLN-D01 | CC-DET-MNT | 2025-02-26 | 2025-03-11 00:00 | 2025-03-11 08:00 | 2025-03-11 14:11 | 2025-03-12 10:11 | 7467.36 | 8146.57 | 114.8 | 131 | OVER | UNKN |  | NT-3000-980103
40300000118 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-COMP-265 | EQ-3000-41182 | 3 | Medium |  | OVHL | Overhaul | CLSD | Closed | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-24 | 2025-02-25 00:00 | 2025-02-26 18:00 | 2025-02-25 10:00 | 2025-02-28 13:00 | 11301.77 | 12516.33 | 45.6 | 47.9 | WEAR | ENVR |  | NT-3000-460549
40300000119 | PM04 | Predictive Maintenance | 3000 | Plant C - Detroit | DET-COMP-481 | EQ-3000-68776 | 4 | Low | MP-3000-050 | CALI | Calibration | PCNF | Partially Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-28 | 2025-03-03 00:00 | 2025-03-05 22:00 | 2025-03-03 00:00 |  | 3476.51 |  | 4.9 |  | NONE
40300000120 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-TURB-259 | EQ-3000-10562 | 3 | Medium |  | CALI | Calibration | TECO | Technically Complete | ELEC-D1 | PLN-D02 | CC-DET-MNT | 2025-03-01 | 2025-03-10 00:00 | 2025-03-12 18:00 | 2025-03-10 00:00 | 2025-03-11 20:00 | 12110.81 | 12110.81 | 36.2 | 43 | OVER | ENVR | X | NT-3000-822622
40300000121 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-PUMP-849 | EQ-3000-72781 | 4 | Low | MP-3000-023 | CALI | Calibration | CNF | Confirmed | MECH-D1 | PLN-D02 | CC-DET-MNT | 2025-02-24 | 2025-02-27 00:00 | 2025-03-02 00:00 | 2025-02-27 00:00 | 2025-02-27 16:00 | 1107.49 | 1402.9 | 74.9 | 107.6 | NONE
40300000122 | PM05 | Emergency Maintenance | 3000 | Plant C - Detroit | DET-PUMP-722 | EQ-3000-94058 | 4 | Low |  | LUBR | Lubrication | CRTD | Created | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-25 | 2025-03-07 00:00 | 2025-03-09 21:00 |  |  | 19641.44 | -500 | 92.5 |  | WEAR | AGE | X | NT-3000-636648
40300000123 | PM03 | Condition-Based Maintenance | 3000 | Plant C - Detroit | DET-CONV-299 | EQ-3000-74286 | 2 | High | MP-3000-025 | REPL | Replacement | TECO | Technically Complete | ELEC-D1 | PLN-D01 | CC-DET-MNT | 2025-02-26 | 2025-03-08 00:00 | 2025-03-10 19:00 | 2025-03-08 00:00 | 2025-03-08 09:00 | 10240.17 | 10240.17 | 86.5 | 112.4 | NONE
40300000124 | PM02 | Corrective Maintenance | 3000 | Plant C - Detroit | DET-TURB-453 | EQ-3000-56052 | 3 | Medium |  | CLEA | Cleaning | TECO | Technically Complete | INST-D1 | PLN-D02 | CC-DET-MNT | 2025-02-26 | 2025-03-06 00:00 | 2025-03-06 13:00 | 2025-03-06 00:00 | 2025-03-07 05:00 | 18667.43 | 19033.87 | 51 | 51 | NOIS | MATL |  | NT-3000-863998